UN Focus Area 1: Inclusive, Equitable and Sustainable Growth

| Draft Outcome 1.1: By 2016, key national institutions formulate and monitor people-centered, green and evidence-based socio-economic development policies to ensure quality of growth as a Middle Income Country |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 1.1.1: Strengthened capacities of data producers, providers and users for evidence-based socio-economic development planning and monitoring |  |  |  |  |  |  |
| Rationale: The information needs for evidence-based planning, policy formulation and M&E have been increasing over the last few years which results in the rising importance of statistical and related activities. However, there still exist many constraints on data producer, provider and user sides in producing, accessing to, and using reliable and timely data/information. There are deficiencies in the implementation of the data collection systems, and technical aspects of statistical work. An improper and insufficient legal framework, institutional and organizational structures are posing difficulties. Coordination including data sharing among the institutions is incomplete. Data dissemination is limited in relation to what is available and what users need and there is no formal data dissemination policy. Some decision and policy makers/leaders are not sufficiently aware of the role of statistics and their own role in statistical activities. Importantly, users’ knowledge of existing data and information is still limited. The General Statistics Office, as a coordinator of the Vietnam’s Statistics System, is developing the Vietnam’s Statistical Development Strategy (VSDS) to 2020 and the Vision to 2025 with concrete action plans and an M&E framework. With the role of a donor coordinator and convener as well as its expertise in developing and guiding statistics work in many statistical areas, the UN system has been supporting different actors within the Vietnam’s Statistics System and data users over the last decades. In 2012-2016, the UN will continue its support to the implementation of the VSDS with focus on the harmonization and coherence of the whole Vietnam’s Statistics System, and to effective utilization of statistics for policy formulation, monitoring, reporting and experience sharing. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.1.1: Strengthened capacities of data producers, providers and users for evidence-based socio-economic development planning and monitoring | Indicator 1: Ranking of Vietnam’s national statistics system (WB/IMF) Baseline (2010): ranking 7/9 in South East Asia Target (2016): medium ranking in South East Asia MoV: M&E framework of Vietnam’s Statistical Development Strategy (annually) Indicator 2: Degree of users’ satisfaction with the quality and timeliness of data provided by the National Statistical System Baseline (2008): 31.3% satisfied Target (2016): 50% satisfied MoV: User survey (expected annually) | - Support the refinement, update and implementation of the Action Plans and M&E framework of the National Statistical Development Strategy. | FAO, ILO, UNDP, UNFPA, UN-HABITAT | MPI, GSO, line ministries/agencies, cities/provinces, social partners |  | 22,330,000 |
|  |  | - Support monitoring, reporting and sharing Vietnam’s experiences to other countries, especially developing countries (South South cooperation) regarding implementation of socio-economic development policies, strategies, plans, MDGs, human development with the focus on the most vulnerable groups. | FAO, ILO, UNDP, UNFPA, UNICEF, UN Women | - Research Ínstitutes, MOLISA, GSO, MPI/DPIs, VASS, MOCST, CEM, NA, PSPMOs (political, social, professional and mass organisations), social partners |  |  |
|  |  | - Support to enhance policy makers and research institutions’ capacity in accessing and using data and information in evidence-based policy formulation and development planning. | - FAO, ILO, UNDP, UNESCO, UNFPA, UNHABITAT, UNICEF, UNIDO | - MOLISA, MPI, GSO, CIEM/DSI, VASS, MoH/VAAC, other research Ínstitutes, PSPMOs, four regional institutes for hygiene and epidemiology, - universities, social partners, MOIT, MOFA, other ministries, Vietnam Urban Development Agency (VUDA/MOC), municipalities, Association of Cities of Viet Nam (ACVN) |  |  |
| Draft Output 1.1.2: Strategic options for development policies defined and considered by policy-makers to promote inclusive, people-centered, and equitable development |  |  |  |  |  |  |
| Rationale: The Socio-Economic Development Strategy (S 000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000002011-2020 (SEDS) with its strategic development directions has been approved at the Viet Nam Communist Party’s XI Congress in January 2011. The Socio-lDS0000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000Economic Development Plan (SEDP) 2011-2015 has been prepared. It is made clear in these documents that in parallel with the significant achievements over the last few years, economic development is not yet sustainable, quality of growth, productivity, efficiency and competitiveness of the economy remain low, and macroeconomic balances not yet really steady. There remain limitations in the mobilization of development resources and their efficient utilization. Economic growth relies on extensive development factors and the shift to intensive development remains slow. Other inadequacies persist in the cultural, social, and environmental fields remain pressing. Problems with market economy institution, human resources quality and infrastructure remain as bottlenecks to development. Foundations for Viet Nam to become a modern-oriented industrialized country have not been fully laid. With the new status of a MIC country and under the effects of global, changing and unpredictable circumstances, there would be a need to identify strategic options and concrete action plans for achievement of the Strategy. The UN system has been supporting the country in developing its SEDS, SEDP and other important sectoral strategies. With the strength of a neutral organization working for human rights, equitable and sustainable growth, the UN agencies together will continue its support to Viet Nam in identifying optimal and strategic development options for the country. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.1.2: Strategic options for development policies defined and considered by policy-makers to promote inclusive, people-centered, and equitable development | Indicator 1: Degree to which research/policy papers of national research/policy institutions are quoted in NA debates Baseline (2011): no citations Target (2016): NA Deputies cite research/policy papers at least in every debate MoV: records of NA debates | - Enhance the national capacity for research and debates on development policy options for the economy’s restructuring, sustainable financing development, pro-poor public resources/investment mobilization, agricultural and rural development, economic integration, private sector development and promoting legal framework for business, effective and efficient labour market and other policies and strategies to effectively response to internal and external shocks, natural disasters, and to adjust to the MIC status. | FAO, UNDP, UN-HABITAT, UNIDO, UN Women | MPI, National Assembly, MOLISA, MOFA, MOH, MOC, WU, other ministries/ agencies, cities/provinces, PPCs of selected provinces, VASS, other research institutes, PSPMOs, universities, social partners , ACVN |  | 22,351,000 |
|  |  | - Provide policy advising and advocacy to national and sub-national levels during the policy/strategy/plan development process leading to inclusive, people-centered, quality, sustainable and equitable development results. | - FAO, IOM, UNAIDS, UNDP, UNESCO, UNIDO | - MPI, National Assembly, MOLISA, MOFA, MPS, MOC, other ministries/ agencies, cities/provinces, PPCs of selected provinces, VASS, other research institutes, PSPMOs, universities, social partners , ACVN |  |  |
|  |  | - Provide international experiences on development options and how coping with internal and external shocks to formulate MIC-related policies, strategies and plans. | - FAO, UNDP, UNIDO, UN Women | - MPI, National Assembly, MOLISA, MOC, other ministries/ agencies, cities/provinces, PPCs of selected provinces, VASS, other research institutes, PSPMOs, universities, social partners, ACVN |  |  |
| Draft Output 1.1.3: A multi-dimensional and human development approach is adopted in the poverty reduction components of socio-economic development plans at national and sub-national level to effectively address chronic and emerging forms of poverty |  |  |  |  |  |  |
| Rationale: Viet Nam has achieved Millennium Development Goal 1 related to the eradication of hunger and extreme poverty. The poverty rate has been decreased constantly and rapidly over the last decade. Nevertheless, the rate is still numerous in certain places, especially in mountainous, remote and difficult areas, and among most vulnerable groups of the population such as ethnic minorities, informal worker, and migrants. Persistent, chronic and newly emerging forms of poverty are more difficult to tackle and will require more creative approaches to deal with. Anti-poverty strategies and programme should incorporate multi dimensions of poverty, in which poverty is targeted and confronted based on not only income but also other social aspects of human lives (e.g. such as access to social security and services). Poverty reduction also needs to be carried out in link with people’s vulnerability to social and economic shocks as well as to climate changes. The UN will support the enhancement of national capacity to formulate and implement poverty reduction strategies and programmes which take into account the multi-dimensional approach and newly-emerging forms of poverty, as well as to mainstream poverty reduction into government policies. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.1.3: A multi-dimensional and human development approach is adopted in the poverty reduction components of socio-economic development plans at national and sub-national level to effectively address chronic and emerging forms of poverty | Indicator 1: Degree to which GoV poverty reduction reports include an analysis of multi-dimensional poverty of vulnerable groups Baseline (2011): only income/ expenditure poverty lines mentioned Target (2016): poverty analysis incorporated MoV: MDG report, poverty updates, reports of NTPs relating poverty reduction multiple dimensions Indicator 2: Degree to which GoV poverty reduction policies specially designed to target chronic and newly emerging forms of poverty Baseline (2011): 135 Programme targeting ethnic minorities Target (2016): policies/programmes targeting different groups of chronic poverty and newly emerging forms of poverty MoV: MDG report, poverty updates, reports of NTPs relating poverty reduction | - Support capacity development for evidence-based and participatory formulation, implementation and M&E of poverty reduction strategies and programmes to effectively address the multi-dimensional nature of poverty, in particular chronic poverty among ethnic minorities and emerging forms of transient poverty among vulnerable groups. | UNDP, UNESCO, UNICEF | MOLISA, CEMA, MPI, GSO, VASS, other ministries/ agencies, cities/provinces, PPCs of selected provinces, social partners , PSPMOs |  | - 15,970,000 |
|  |  | - Provide policy advice to address chronic, transient, and emerging forms of poverty including urban poverty, poverty among migrants, and poverty among informal workers. | - IOM, UNDP, - UNICEF | - MOLISA, CEMA, MPI, GSO, VASS, other ministries/ agencies, cities/provinces, PPCs of selected provinces, social partners , PSPMOs |  |  |
|  |  | - Advocate and provide advice to the mainstreaming of poverty reduction efforts in the design and implementation of relevant sector policies and plans. | - FAO, UNDP, - UNICEF | - MOLISA, CEMA, MPI, GSO, VASS, other ministries/ agencies, cities/provinces, PPCs of selected provinces, social partners , PSPMOs |  |  |
|  |  | - Provide support to strengthen capacity at both national and sub-national levels for implementation of pro-poor and pro-employment policies and plans | - FAO, UNDP | - MOLISA, CEMA, MPI, GSO, VASS, other ministries/ agencies, cities/provinces, PPCs of selected provinces, social partners , PSPMOs |  |  |

| Draft Outcome 1.2: By 2016, institutions create opportunities for decent work for people of working age, particularly the most vulnerable and disadvantaged, to benefit in the process of socio-economic transformation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 1.2.1: Inclusive policies and programmes for sustainable enterprise development are created and implemented with particular focus on micro and small enterprises, for decent job creation and progressive formalization of the informal sector |  |  |  |  |  |  |
| Rationale: Sustainable enterprises are the principal source of growth, wealth creation and employment, and play a critical role in poverty reduction. Especially micro, small and medium sized enterprises are one of the main instruments of job creation but these are often characterized by insufficient work and environmental practices. It is pivotal to support the creation of an environment that combines the legitimate quest for profit with the need for development, which respects human dignity, environmental sustainability and decent work. The UN will support national and sub-national private and public actors in creating a business environment conducive to business growth, providing a level playing field. It will support business development services and professional associations in providing services and enter into dialogue with the Government. And strengthen the application of economically, socially and environmentally sustainable enterprise-level practices. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.2.1: Inclusive policies and programmes for sustainable enterprise development are created and implemented with particular focus on micro and small enterprises, for decent job creation and progressive formalization of the informal sector | Indicator 1: Number of businesses registered in selected provinces Indicator 2: Capacity of a system to assess the extent to which enterprises and factories follow labour standards Baseline (2010): No independent system Target (2016): System in place to assess the extent to which enterprises and factories follow labour standards is independent and self sustaining | - Support the improvement of the business enabling environment to become inclusive, competitive and transparent for all components of society and to the wider utilization of good corporate governance practices | ILO, ITC, UNIDO | MOLISA, MPI, VCCI, VNAT, sub-national governments, Business Registration Offices |  | 13,456,000 |
|  |  | - Support professional/sectoral organisations to participate in the formulation and implementation of enterprise development and decent job creation policies and programmes including the informal and service sector | - ILO, ITC | - MOIT, DOIT, VIETCRAFT, VIETRADE |  |  |
|  |  | - Strengthen professional associations, business development organizations and trade support institutions to enable them to provide an appropriate and sustainable range of specialized services for enterprise start-up and development | - ILO, ITC, UNIDO | - VCCI, LEFASO, VITAS, VEIA, EuroCham, General Department of Standards, Metrology and Quality, ILLSA, MTEC, SEQUA |  |  |
|  |  | - Strengthen the application of economically, socially and environmentally sustainable enterprise-level practices | - ILO, ITC | - MOLISA, MOIT, VCCI, PPCs, DOLISA, DOIT |  |  |
| Draft Output 1.2.2: Vocational and skills training policies and programmes are of high quality, accessible and respond to market needs |  |  |  |  |  |  |
| Rationale: With the development of the economy, Viet Nam is facing ever increasing competition, which requires raising of the skill level of the labour force by equipping them with quality working skills demanded by the market. Current studies and observations show that there is a mismatch between supply and demand of working skills, and the lack of higher level technical and managerial skills. This requires the development and implementation of evidence-based vocational training policies and programmes with focus on identified Vocational Education and Training (VET) administration, more autonomy of VET service providers, a new skills development system, proper training models/standards and strengthened training institutions. The UN will support the enhancement of national capacities in developing and implementing evidence-based VET policies and programs, a skills development system, proper training models/standards, a core of world class Vietnamese trainers/enterprise counselors and improved accessibility to training by vulnerable groups, particularly women, as well as a defined role of the State in VET administration for a high-quality and competitive labour force. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.2.2: Vocational and skills training policies and programmes are of high quality, accessible and respond to market needs | Indicator 1: A National Qualifications Framework (NQF) developed Baseline (2011):0 Target:1 MoV: Indicator 2: Number of skills standards in high demand areas issued within the national qualifications framework Baseline (2011): Target (2016): 80 new ones MoV: GDVT (General Director of Vocational Education) | - Support the development and implementation of skills development system that meets the labour market requirements and is accessible to vulnerable and disadvantaged groups, particularly women and those in informal economy | ILO, UNESCO | MOLISA, MOET, MPI, VNAT, DOLISAs |  | 3,400,000 |
|  |  | - Support the development and implementation of government and non-government vocational training skills development programmes and services that foster workplace learning and meet the needs of and are accessible to vulnerable and disadvantaged groups, particularly women and those in informal economy | - ILO | - MOLISA, MOET, DOLISAs, Women’s - Union |  |  |
|  |  | - Strengthen training institutions and develop a core of world class Vietnamese trainers/enterprise counselors to provide market-driven and quality higher (management and technical) training and counseling services through enhanced partnership with (national and foreign) training institutions and businesses | - ILO, ITC | - MOLISA, MOET, DOLISAs, VCCI |  |  |
| Draft Output 1.2.3: Competitiveness and market access are improved for formal and informal sector actors in compliance with standards, based on advanced knowledge and services on trade, investment and technology |  |  |  |  |  |  |
| Rationale: To be globally competitive, the formal and informal sectors need not only an enabling business environment and skilled labor force but also better access to business opportunities, capital, technology, information, new business models/approaches and other inputs to different extents. Deeper integration into the world economy requires pro-active approaches that will enable Viet Nam to reap the full benefits of participating competitively in the global economy, in particular being able to respond to the more and more complex requirements of particular segmented export markets. The UN will strengthen national capacities to provide customized support services in areas such as trade promotion and facilitation; market information systems; technology transfer; standards, testing and certification; investment promotion and linkages; business development services, which can lead to qualitative improvements in the country’s competitiveness in world markets. This will be achieved by enhancing technology and knowledge transfers associated with trade and investment, promoting greater competitiveness and facilitating the insertion of local producers into global production systems and value chains. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.2.3: Competitiveness and market access are improved for formal and informal sector actors in compliance with standards, based on advanced knowledge and services on trade, investment and technology | Indicator 1: Number of companies that have registered under a certain (new) business standard (Vietnamese or ISO) Baseline (2011): Target (2016): MoV: | - Assist Government, enterprises and other stakeholders to assess the export potential of Viet Nam vis-à-vis international demand, trade related obligations, and present and future export opportunities | - ITC, UNIDO | MOIT, VCCI, VIETCRAFT, MARD, MOCST, Research Institutes |  | 15,100,000 |
|  |  | - Promote the gender sensitive value chain and cluster approaches to ensure that concerned stakeholders, particularly women, are able to create and add value to their operations including by becoming part of global value chains | - FAO, ILO, ITC, UNESCO, UNIDO | - PPCs of selected provinces, MOLISA, DOLISAs |  |  |
|  |  | - Enhance competitiveness of businesses in formal and informal sectors by facilitating their access to knowledge and services concerning end market requirements, including labour and environmental standards, strategic planning, resource management, technology, product development and how to reach target customers through the right channels | - FAO, ILO, ITC, UNIDO | - MOIT, MPI, MOLISA, DOLISAs |  |  |
| Draft Output 1.2.4: Employment policies, programmes and services are strengthened to prevent and address discrimination and exploitation of workers going abroad and other vulnerable groups |  |  |  |  |  |  |
| Rationale: Challenges exist in relation to development and implementation of overseas employment management laws, policies and mechanisms for human development, accessibility and availability of services, particularly on addressing discrimination and exploitation related concerns as specified in UN analysis. Human trafficking for labour and sexual exploitation, associated with the increased migration and mobility, are viewed as serious problems in the newly adopted Anti-trafficking law and in the SEDP 2011-2015. Deliberate policies and practices by the State and concerned stakeholders are required to ensure that migration benefits Vietnam and the migrants themselves. Stigma, discrimination and exploitation still prevent full access and participation of vulnerable people in the labour market, especially women and migrant labourers, both of whom tend to work in more disadvantaged conditions in the informal sector. Women are also affected by persistent gender wage gaps, they continue to face both direct and indirect discrimination in the labour market, and they are overrepresented in vulnerable and in invisible employment. The UN will support the government and related key stakeholders to strengthen legislative and regulatory frameworks to manage overseas employment and protect rights of migrant and women workers, to create more accessible services for migrant workers and to address specific needs of other vulnerable groups in line with international standards and conventions. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.2.4: Employment policies, programmes and services are strengthened to prevent and address discrimination and exploitation of workers going abroad and other vulnerable groups | Indicator 1: Number of sub-laws developed and amended in line with international standards to facilitate the implementation of the Law on Contract-Based Overseas Workers Baseline (2011): 13 existing sub-laws (decree, circular, decision) Target (2016):16 existing sub-laws (3 new developed) 5 amended MoV: Project and donor reports Indicator 2: Extent to which women and men migrant workers are aware of their rights and of the safe migration Baseline (2011): first survey conducted and information available by end of 2011 Target (2016): 5,000 migrants to have a have good awareness of how to protect themselves from labour exploitation MoV: ILO Triangle bi-annual surveys until 2015 | - Support the development, implementation and monitoring of labour protection, overseas employment, and anti-discrimination strategies, laws, policies and mechanisms including the regulations of recruitment and support services for migrant workers | ILO, IOM, UN Women | MOLISA, MOJ, MPS, Women's Union, VCCI, VGCL, VCA |  | - 3,650,000 |
|  |  | - Support the government and other key stakeholders in developing or strengthening policies and mechanisms that enhance the positive impacts of overseas employment for human development | - ILO, IOM, UN Women | - MOLISA, MOJ, MPS, Women's Union, |  |  |
|  |  | - Improve access to information on safe migration and support integrated services for domestic and international labour migrants, particularly those within and withdrawn from exploitative conditions | - ILO, IOM | MOLISA, PSPMOs, Manpower organisation, MOJ, MPS, Women's Union, VCCI, VGCL, VCA, PCSA |  |  |
|  |  | - Support line-ministries and other key stakeholders to strengthen the legal and policy response, and the service provision to increase the equality and access to opportunities in the labour market for PLHIV, women and disabled people. | - ILO, UN Women | - MOLISA, Research Institutes (VASS), MOLISA, MOJ, MPS, Women's Union, VCCI, VGCL, VCA |  |  |

| Draft Outcome 1.3: By 2016, key national and sub-national agencies, in partnership with the private sector and communities, have established and monitor multi-sectoral strategies, mechanisms and resources to support implementation of relevant multilateral agreements and effectively address climate change adaptation, mitigation and disaster risk management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Draft Output 1.3.1: Planning and investment processes are climate proofed and specific programs have been formulated and operationalised for long term adaptation to reduce climate change vulnerabilities |  |  |  |  |  |  |  |  |  |  |
| Rationale: Viet Nam will face significant development challenges caused by climate change, which will trigger long term changes in human development and ecology. Climate change, related disasters and resulting migration pressures figure among the most serious challenges Viet Nam is facing. Thus climate proofing of development plans and strategies is needed. Further research on the impact of climate change on migration patterns, agriculture, livestock, gender relations and vulnerable communities is seen as crucial for proper strategy development. The work under this output will also focus on drought as drought is increasingly critical in Viet Nam, especially in some of the poorer areas in the South Central Coast where desertification has become an issue. This will build on UNDP, FAO, and IFAD strengths and capacity in the country to address drought and desertification/land degradation. Viet Nam recognizes that climate change adaptation is critical and has shown commitment to mainstreaming climate change adaptation and climate proofing in its SEDP and SEDS planning framework, but lacks relevant capacities. |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators |  | Draft Key Actions | UN Agencies | Partners |  |  | Assumptions | Indicative Budget (US$) |  |
| Output 1.3.1: Planning and investment processes are climate proofed and specific programs have been formulated and operationalised for long term adaptation to reduce climate change vulnerabilities | Indicator 1: Number of new circulars and guidelines issued that effectively enable planners and policy makers to climate proof their development plans and investments Baseline (2011): Target (2016): MoV: Indicator 2: Percentage of additional budget allocation to climate change adaptation in the agricultural sector and for migration /resettlement, compared to baselines at national level |  | - Support formulation of new legal instruments to enable effective mainstreaming of climate change adaptation in development and investment planning, including for: - Urban planning regulations - Land use regulations/land law review - City development plans - Provincial land use plans - Large infrastructure investments - Resettlement/relocation programs - Land/dry land management and desertification issues. - Mainstream climate change into building codes with emphasis on vulnerable group housing - Mainstream climate change adaptation in relevant laws (disaster risk management, land law, urban law, etc.) | FAO, IFAD, IOM, UNDP, UN-HABITAT, UN Women | MPI, MARD, MoNRE, MoIT, MoC, MoLISA and MoET, provinces, municipalities, PSPMOs (e.g.Viet Nam Women’s Union), research institutes, sub-national Government authorities |  |  |  | 16,520,000 |  |
|  |  |  | - Support policy formulation, programming and capacity building for relevant duty bearers and right holders, for sustainable resettlement and climate change and other environmentally induced migration, based on past lessons learnt and additional research with due respect to the preservation of the culture of the population involved | IOM, UNDP, UNEP, UNESCO, UN Women | - MoNRE, MARD - VWU, NA - PPC, MoLISA, sub-national Government authorities |  |  |  |  |  |
|  |  |  | - Facilitate research on climate change effects and impacts on agriculture, livestock adaptation and industrial and appropriate urban development policy options for medium to long term climate change adaptation ensuring that indigenous knowledge is acknowledged | FAO, UNDP, UN Women | - MoNRE - MARD - Vietnam Women’s Union (VWU) - National Assembly, - research institutes |  |  |  |  |  |
|  |  |  | - Provide technical assistance on mainstreaming climate change adaptation to initiate and implement policies focused on planning and investment, environment/natural resource management, rural and urban development and local action plans. | FAO, IFAD, UNDP, UNESCO, UN-HABITAT, UNV | - MPI, MoNRE, MARD, MoC, sub- national Governments and research institutes |  |  |  |  |  |
| Draft Output 1.3.2: Resilience of at-risk and vulnerable groups to natural hazards is enhanced, and nationally relevant aspects of international agreements on disaster risk management are implemented |  |  |  |  |  |  |  |  |  |  |
| Rationale: Viet Nam faces significant exposure to disasters. The country lost, on average, 1-1.5% of GDP (based on PPP) over the last 20 years. Viet Nam ranks fifth globally in terms of overall material losses and mortality from climatic disasters. The Government has promulgated a Decision on community based disaster risk management and has asked for UN assistance in the operationalisation of this program. The Government is working on a law on disaster risk management (with UN support) which will embed international commitments, such as the Hyogo Framework for Action (HFA) and the ASEAN Agreement on Disaster Management and Emergency Response, to address the needs of those at risk. |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators |  | Draft Key Actions | UN Agencies | Partners |  | Assumptions |  |  | Indicative Budget (US$) |
| Output 1.3.2: Resilience of at-risk and vulnerable groups to natural hazards is enhanced, and nationally relevant aspects of international agreements on disaster risk management are implemented | Indicator 1: Percentage participation of vulnerable groups (e.g. women, ethnic minorities and displaced people) institutionalised in disaster related decision making processes for sub-national level preparedness, response and early recovery activities (including risk assessments) Indicator 2: Percentage of targeted communities, national and sub-national Government and Central Committee for Flood Storm and Control (CCSFC) members that show increased knowledge of CBDRM |  | - Support capacity building for the implementation of the Government’s Decision 1002 on CBDRM (Community Based Disaster Risk Management), at national and sub-national level in both rural and urban contexts, especially amongst Government and Mass Organization cadres (including participatory disaster risk assessment, monitoring and evaluation at local level to address the specific needs and rights of vulnerable groups) | IOM, UNDP, UNEP, UN-HABITAT, UNICEF, UNV, UN Women | MARD, MPI, MoNRE, MoH, MoLISA, VWU, Viet Nam Red Cross Society (VNRC), provinces and municipalities, universities, sub-national Governments, PSPMOs |  |  |  |  | 10,410,000 |
|  |  |  | - Support the implementation of other aspects of the Hyogo Framework for Action, including the establishment and development of a National Platform for disaster risk reduction and climate change adaptation, strengthening early warning and knowledge generation including risk mapping taking into account cultural factors and acknowledging indigenous knowledge | - FAO, UNDP, UNESCO, UNICEF, UN Women, WHO | - VWU , MoLISA, MARD, MoH, MoET, MPI, - MoNRE - MoH |  |  |  |  |  |
|  |  |  | - Strengthen disaster risk management capacity in the agricultural sector which involves the development of drought, nutrient efficient and flood resistant crop varieties, livestock disease and the development of a series of tools in preparedness is being developed with the Government and includes hazard mapping | - FAO, UNDP | - MARD |  |  |  |  |  |
|  |  |  | - Facilitate duty bearers to undertake appropriate applied research and formulate good practice derived from lessons learnt in CBDRM for further policy development | - UNDP, UN Women | - MARD, PSPMOs |  |  |  |  |  |
|  |  |  | - Maintain and mobilize capacity to respond to medium and large scale humanitarian disasters, coordinating and sharing information on the emergency response and early recovery, in support of the GoV. | - UNDP, UNICEF, UN Women | - MARD, MPI, MoF, MoH, MoC, PSPMOs |  |  |  |  |  |
| Draft Output 1.3.3: A national system for Reduced Emissions from Deforestation and forest Degradation (REDD), and Nationally Appropriate Mitigation Actions (NAMAs) for a number of strategically chosen sectors and localities are formulated and operationalised with clear potential benefits |  |  |  |  |  |  |  |  |  |  |
| Rationale: An important agreement under the UNFCCC in Cancun (2010) is the development of NAMAs by developing countries, especially those that would receive international technical and financial support. NAMA design and submission to a forthcoming register is critical for achieving this. It is crucial that efforts on formulation of NAMAs and their implementation address general energy efficiency, enhancement of renewable energy production, and take into account energy needs of the poor. An effort to develop sustainable energy access for marginalized and vulnerable communities is critical for achieving the MDGs. Significant agreements on REDD were also reached in Cancun. Viet Nam is a lead country on preparing for REDD with support from the UN-REDD program, and can deliver on GHG emission reductions from the forestry sector if this program is successful as per the current draft design of a substantial pilot and further development of national REDD. |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators |  | Draft Key Actions | UN Agencies | Partners |  |  | Assumptions | Indicative Budget (US$) |  |
| Output 1.3.3: A national system for Reduced Emissions from Deforestation and forest Degradation (REDD), and Nationally Appropriate Mitigation Actions (NAMAs) for a number of strategically chosen sectors and localities are formulated and operationalised with clear potential benefits |  | Indicator 1: Number of subsectors/ cities/towns/provinces with NAMAs developed and submitted to an international register Indicator 2: GHG emissions reduced as compared with BAU for the forestry sector | - Support research and formulation and implementation of the national REDD plus strategy and system (through UN-REDD) | FAO, UNDP, UNEP, UNESCO, UNODC, UNV, UN Women | MARD, MoNRE, MPI, MoF, PSPMOs |  |  |  | 27,850,000 |  |
|  |  |  | - Support research on sectoral NAMA development and the formulation of at least three major manufacturing sub-sectors and submit the NAMAs for international support and technology transfer | - UNDP, UNIDO | - MoNRE, MPI,MoIT, MoC, private sector |  |  |  |  |  |
|  |  |  | - Support research and formulate area based NAMA development piloted for at least three cities/towns and submit the NAMAs for international support and technology transfer | - UNDP, UN-HABITAT | - MPI, MONRE, HCMC, Hanoi, Da Nang, PSPMOs, private sector |  |  |  |  |  |
|  |  |  | - Support NAMA research and development for agricultural subsectors including wet land rice production and livestock production and submit the NAMAs for international support and technology transfer | - FAO, UNDP | - MPI, MARD, MoNRE |  |  |  |  |  |
|  |  |  | - Provide technical assistance and research to support the development of domestic carbon markets in particular pro poor elements | - FAO, UNDP, UNEP, UNIDO | - MPI, MoNRE |  |  |  |  |  |
| Draft Output 1.3.4: National long term climate change strategy and Green Economy/low carbon strategy operationalised which are based on the national development vision (SEDS) while building on the National Target Programme results |  |  |  |  |  |  |  |  |  |  |
| Rationale: The international community has progressed significantly in developing a comprehensive climate change response during COP 16 in Cancun in 2010. Viet Nam has actively participated in international climate change negotiations but additional (institutional) capacities on climate policy are critical for it to reach its full potential. Viet Nam has requested the UN to assist in the development of a comprehensive climate change strategy building on existing programs such as the NTP-RCC and the SPRCC. Recent agreements under the UNFCCC in particular call on countries to development comprehensive climate change response strategies and specifically a national adaptation plan, a low carbon development strategy, and NAMAs. These are important elements of a future climate change response regime as has been given shape during the Cancun UNFCCC COP 16. The importance of a coherent strategy is significant as it will enable Vietnam to bring together current activities. This involves the NTP-RCC, SP-RCC, NTP-energy efficiency, REDD plus and a significant number of research activities. The strategy as well will ensure that climate change policy is aligned with the national development priorities and vision as are outlined in the Social Economic Development Strategy (SEDS). An overall strategy and the specific policy instruments for adaptation and mitigation must help prioritize climate change related policies and investments both from domestic as well those financed from international resources. |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators |  | Draft Key Actions | UN Agencies |  | Partners |  | Assumptions | Indicative Budget (US$) |  |
| Output 1.3.4: National long term climate change strategy and Green Economy/low carbon strategy operationalised which are based on the national development vision (SEDS) while building on the National Target Programme results | Indicator 1: A national climate change strategy and a full MRV system developed, approved by the Government, and submitted to the UNFCCC Indicator 2: Annual national budget allocation for adaptation actions, DRR, and domestic mitigation actions as percentage of total Government budget |  | - Support research towards the formulation and implementation of a national climate change strategy, comprising internationally agreed elements such as the National Adaptation Plan (NAP) and Green Economy/low carbon development strategy (and that prioritizes and enables adaptation actions, NAMAs, and REDD plus) | UNDP, UNICEF |  | MPI, MoNRE, MARD, MoT, MoFA, MoET, CEM, MoLISA, MoH,sub-national Government authorities |  |  | - 2,670,000 |  |
|  |  |  | - Support establishment of Monitoring Reporting and Verification (MRV) system related to the national strategy, REDD and NAMAs, and build capacities to implement and operate MRV | - FAO, UNDP |  | - MoNRE, MARD, MoIT, MPI, PSPMOs |  |  |  |  |
|  |  |  | - Support the institutional development, capacities and implementation of research on climate change, specifically the “scientific basis” and formulation of scientific advice to policy makers | - UNDP, UNEP, UNESCO, UN-HABITAT, WHO |  | - MoNRE, MARD, MoH, MPI, MoIT, MoC, MoST |  |  |  |  |
|  |  |  | - Facilitate convening and coordination mechanisms on climate change policy. | - UNDP, UNESCO, UN Women |  | - MoNRE, MARD, MoET, PSPMOs |  |  |  |  |
|  |  |  | - Build capacities, networks and partnerships for effective Vietnamese participation in international climate policy processes | - UNDP, UNEP, UNESCO, UNV |  | - MoNRE, MARD, MPI, MoIT, MoC, PSPMOs |  |  |  |  |
|  |  |  | - Provide capacity building for media to ensure effective monitoring and reporting of the National Climate Change Strategy implementation | - UNDP, UNEP, UNESCO |  | - Media (including: international and national TV and press agents) |  |  |  |  |

| Draft Outcome 1.4: By 2016, key national and sub-national agencies, in partnership with the private sector and communities, implement and monitor laws, policies and programmes for more efficient use of natural resources and environmental management, and to implement commitments under international conventions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 1.4.1: Policies, regulations and fiscal tools for green economic development, natural resources management and cleaner production are formulated and applied |  |  |  |  |  |  |
| Rationale: Rapid economic growth (6.68% in 2010) and industrialization require using more natural resources. It is important to adopt cleaner production, increase efficient use of natural resources, and reduce environmental pollution to produce one unit of economic output/GDP. Market-based regulations and fiscal tools will help create a level playing field for all stakeholders in exploitation of natural resources. It will help direct resources to the production process and stakeholders where they can be most effectively used. The Ministry of Natural Resources and Environment (MONRE) adopted a party resolution (sub-party committee in MONRE) on economization of the natural resources and environment sector which attempts to introduce and apply market-based tools. Urbanization and industrialization are happening very rapidly in Viet Nam. There are some overlapping planning processes led by different ministries, such as overall land management by MONRE, construction planning by MOC, rural development planning by MARD, etc. so it is essential to adopt integrated planning for development to meet the needs of the poor and disadvantaged groups. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.4.1: Policies, regulations and fiscal tools for green economic development, natural resources management and cleaner production are formulated and applied | Indicator 1: Number of new regulations/ tools adopted to enhance spatial planning at national and target provinces Indicator 2: Number of companies and households that apply cleaner (green) production models | - Facilitate evidence-based research, support the development of market-based policies and fiscal tools, enhance the capacity to implement and monitor the implementation of policies, laws and programmes for effective management and efficient use of natural resources and cleaner production. | UNDP, UNEP, UNIDO | MONRE, MARD, MOIT, MOC, ISOPNR, MPI |  | 11,695,000 |
|  |  | - Support government authorities to adopt green economic development models, and integrated planning and management tools for sustainable urban and rural development at target provinces, for the benefits of the poor and vulnerable groups. | - IFAD, UNDP, UN-HABITAT, UNIDO, UNV | - PPCs of selected provinces, MARD, MPI, Quang Nam city, Local municipalities, People’s Committees |  |  |
|  |  | - Support to build more resource efficient and cleaner production models/technologies in industrial, agricultural and handicraft sectors. | - FAO, IFAD, UNEP, UNIDO, UNV | - MoNRE, PPCs of selected provinces, MARD, MPI, MOIT |  |  |
|  |  | - Advocate with decision makers and raise awareness among general public on green economic development, sustainable consumption, and pro-environmental behaviour. | - UNDP, UNESCO, UN-HABITAT | - MONRE, MARD, MOIT, Local municipalities, People’s Committees |  |  |
| Draft Output 1.4.2: A set of coherent plans are prepared or updated to strengthen (1) Management of Protected Areas and biodiversity conservation, and (2) environment management at national and community levels |  |  |  |  |  |  |
| Rationale: Viet Nam is signatory to a number of major multilateral environmental agreements, including the UN biodiversity convention which sets global target to reduce biodiversity loss by 2010 (this was revised late 2010). Unfortunately biodiversity loss continues at global level and in Viet Nam. Viet Nam is also committed to achieve the MDGs, but is currently not on track to meet MDG7/VDG targets (as per the National Report on progress towards the MDGs, which Viet Nam published in 2010), including biodiversity conservation, protection of key habitats (including PA systems) and sustainable exploitation of natural resources. Viet Nam has a good establishment and operation of the terrestrial/ forest protected areas, initial success in operation of the marine and coastal protected area, but has yet establish a full system of wetland protected areas for biodiversity conservation and protection of key habitats in line with international conventions. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.4.2: A set of coherent plans are prepared or updated to strengthen (1) Management of Protected Areas and biodiversity conservation, and (2) environment management at national and community levels | Indicator 1: A new financing mechanism for PA systems and biodiversity conservation Indicator 2: More finance allocated from the State budget and attracted from international and business for biodiversity conservation and PA system | - Support the revision and development of plans and policies for establishment and management of a wetlands PA system. | UNDP, UNEP | MONRE, MARD, MOF |  | - 13,434,000 |
|  |  | - Provide technical assistance to the design, establishment, and opertionalisation of a sustainable financing mechanism to attract more finance for effective management of PA systems and biodiversity conservation efforts. | - FAO, UNDP, UNESCO | - MONRE, MARD |  |  |
|  |  | - Support the institutional development, policy formulation and implementation to enhance actions for biodiversity conservation. | - UNDP, UNEP, UNESCO, UNV | - MoNRE, MARD |  |  |
|  |  | - Support the community-based projects on efficient use of natural resources, effective environmental management, and climate change at local levels to improve community livelihoods, in partnership with PSPMOs. | - UNDP, UNEP, UNESCO, UNV | - MoNRE, PSPMOs |  |  |
| Draft Output 1.4.3: Policies, plans, and technical skills are strengthened for the sound management of hazardous chemicals and persistent organic pollutants (POPs), in accordance with international conventions |  |  |  |  |  |  |
| Rationale: Viet Nam is a signatory to the Basel Convention on the Control of Transboundary Movements of Hazardous Wastes and their Disposal, and Stockholm Conventions on Persistent Organic Pollutants (POPs) and Rotterdam Conventions & Code of Conduct for Distribution and Use of Pesticides). The American war left behind huge challenge of dioxin contamination and the past development also left behind a large amount of obsolete POPs, including pesticides. Environmental treatment of these POPs/hazardous waste requires specialized technical knowledge, technologies, and a large amount of funding. Capacity, technical knowledge and technologies for the government in this area will not only be important for phasing out of existing POPs, but also important for sound management of hazardous waste and chemicals and treatment of POPs generated from industrialization and the development process in future. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.4.3: Policies, plans, and technical skills are strengthened for the sound management of hazardous chemicals and persistent organic pollutants (POPs), in accordance with international conventions | Indicator 1: Number of key institutions who demonstrate adequate technical knowledge and skills, and apply internationally recognized technologies in environmental remediation of hazardous wastes/chemicals and POPs. Indicator 2: Number of tones POPs treated and hazardous chemicals eliminated. | - Support revision and preparation of the national plans and policies for implementation of Basel, Stockholm and Rotterdam Conventions. | FAO, UNDP, UNIDO | MONRE, MOD, MARD, MOF (customs office), MOIT, provinces MONRE, MOIT |  | 18,069,000 |
|  |  | - Strengthen capacity of the key ministries and agencies in application of environment- friendly technologies, and international BAT/BEP methodologies for sound management of chemicals and phasing out dioxin, pesticides, medical waste, electronic wastes and other POPs. | - UNDP, UNEP, UNESCO, UNIDO | - National Ozone Unit. - Ministry of Finance (General Department of Vietnam Customs), MONRE, MARD |  |  |
|  |  | - Support central and local governments to formulate and implement policies for waste management in craft villages. | - UNESCO, UNIDO, UNV | - MONRE, PPC, MoCST/DoCST |  |  |
|  |  | - Support the coordination and cooperation among countries in the region and among national ministries in management and control of transboundary movement and disposal of hazardous wastes, e-wastes and POPs. | - FAO, UNDP, UNESCO - UNIDO | - MONRE, MARD |  |  |
| Draft Output 1.4.4: Regulations and fiscal tools formulated and operationalized to enhance rights of the land holders, improve land use and water resources management, and enhance access to decent and social housing by the poor and vulnerable groups |  |  |  |  |  |  |
| Rationale: MDG 7 includes another important target, reducing slums and increasing access to social and decent housing by the poor and vulnerable groups in coming years, though the government has adopted some useful policies enable business to participate in building social housing for the poor in recent years. Proper water resources planning management will help tp improve water supply for the poor and vulnerable groups. Viet Nam is facing many challenges in land use planning and management, especially land speculation and lack of user rights of farmers in relation to their farming lands. Addressing these key challenges will enable farmers, the poor and vulnerable groups to benefit more from development. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 1.4.4: Regulations and fiscal tools formulated and operationalised to enhance rights of the land holders, improve land use and water resources management, and enhance access to decent and social housing by the poor and vulnerable groups. | Indicator 1: Number of new regulations/ tools adopted to improve land use, water resources management and housing development. Indicator 2: Number of the poor and the vulnerable groups in target province accessible to decent houses or housing financing schemes. | - Facilitate researches on land policies and markets and management of water resources, land use, and housing. | UNDP, UN-HABITAT | MARD, MOLISA, MOIT, MONRE, MOC/VUDA, ACVN, Research Institutes and Universities (IDS, CIEM, VASS), National Steering Committee on Real Estate and Housing |  | 3,930,000 |
|  |  | - Support to the revision and development of national and provincial plans and policies to improve land use planning, water resources management and increase access to social and decent housing by the poor and vulnerable groups. | - UNDP, UNESCO, UN-HABITAT | - MONRE, MARD, PPC, MOC/ VUDA, ACVN, Research Institutes and Universities (IDS, CIEM, VASS), National Steering Committee on Real Estate and Housing |  |  |
|  |  | - To enhance capacity and coordination at national and provincial levels in formulation and implementation of policies, including fiscal tools for effective management and development of water resources and land. | - FAO, IFAD | - PPCs of selected provinces, MARD, MPI |  |  |

| - Rationale: In this area, UN support will focus on the availability of data and evidence linked to the social protection system. The UN will support the generation of knowledge and a better understanding of emerging risks and vulnerabilities, which is critical in light of Viet Nam’s progressive integration in the global economy, the increasing mobility of the population, and the increased exposure to internal and external shocks, including as a result of climate change. These key actions address the current scarcity of strategic information and knowledge on the nature of risks, resilience of different social groups and vulnerability in Viet Nam. They contribute to ensure an up to date and relevant evidence-base for social protection policy. UN support will also address the analysis, monitoring and evaluation of social protection policies. The M&E framework should provide disaggregated data by region, gender and ethnic groups, so that the social protection system can provide better protection to the most vulnerable groups and address implementation challenges. This will necessarily include capacity development in view of the current absence of an overall integrated M&E framework and approach for social protection, including capacity for real-time monitoring of shocks. Work in this area will bear a close linkage with UN support for broader socio-economic development monitoring under Focus Area 1. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| 2.1.1: High-quality and disaggregated data are available for use by decision-makers to inform the formulation, monitoring and evaluation of social protection related legislation and policy | Indicator 1: Extent to which relevant research findings and recommendations have been discussed and considered useful in the appropriate policy fora Baseline (2011): Policy-makers have limited access to research findings on emerging risks and vulnerabilities Target (2016): Findings of agreed UN research projects discussed and considered by policy-makers MoV: One Plan Annual Reports Indicator 2: Availability of a framework and operational guidance for integrated M&E of the national social protection strategy Baseline (2011): M&E framework not available Target (2016): Framework and operational guidance for social protection M&E available MoV: One Plan Annual Reports | - Support to research on emerging risks and vulnerabilities – in particular climatic, economic, and health-related shocks – as well as on specific issues related to resilience, needs, access and use of social protection services by vulnerable and disadvantaged groups | FAO, ILO, IOM, UNDP, UNFPA, UNICEF, UNODC, UN Women | MOLISA, research institutions, GSO, CEMA, MPI, MOF, MOJ, MARD, MOCST, MPS, selected provinces |  | 9,200,000 |
|  |  | - Support to impact and effectiveness analysis of social protection policies and services | ILO, UNDP, UNFPA, UNICEF, UNODC, UN Women |  |  |  |
|  |  | - Support to the development of an integrated information, planning, monitoring and evaluation system for social protection. | UNDP, UNICEF, UN Women, UNODC |  |  |  |
| Draft Output 2.1.2: Policy advice and technical support provided and considered by the Government to operationalise the national social protection strategy |  |  |  |  |  |  |
| - Rationale: Under this output, UN support will contribute to an integrated and comprehensive social protection system through enhancing the currently weak linkages between the various pillars of the social protection strategy and coherence with relevant policy frameworks, in particular the socio-economic development, labour market, climate change, and poverty reduction strategies. This is a critical prerequisite for achieving broader human development objectives, ensuring equal opportunities for full participation in the labour market and avoiding fragmentation of the social protection system. Explicit linkages as well as integration of evidence related to existing and emerging risks and vulnerabilities - like climate change and economic shocks - will have to be a key feature of the social protection action plans that will represent the cornerstone of the operationalisation, at national and sub-national level, of the national social protection strategy in the coming years. The UN will also provide information about current policy debates that affect all social protection policies, like social differentiation, targeted versus universal approaches and socialisation. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| 2.1.2: Policy advice and technical support provided and considered by the Government to operationalise the national social protection strategy | Indicator 1: Extent to which alternative policy and financing options for universal targeting have been discussed and considered in the appropriate policy fora Baseline (2011): Policy and financing options for universal targeting not available Target (2016): Relevant policy and financing options for universal targeting made available and discussed in appropriate policy fora MoV: Study and analysis reports, policy dialogue documentation Indicator 2: Extent to which national and sub-national action plans reflect linkages between the social protection pillars and coherence with the Socio-Economic Development Strategy and other major policy frameworks as well as address emerging vulnerabilities and risks using disaggregated demographic and socio-economic data Baseline (2011): Social protection action plans not available Target (2016): National and sub-national social protection action plans reflect relevant linkages and address emerging vulnerabilities and risks MoV: National and sub-national social protection action plans | - Support to and advocacy for the development of policy and financing options for universal targeting, including involvement of non-state actors in the provision of social protection | ILO, UNDP, UNICEF, UNODC | MOLISA, MPS, MOH,MOF, MPI, CEMA, MOH, MARD, MONRE, MOCST, relevant NA committees, research institutions |  | 6,350,000 |
|  |  | - Support to and advocacy for strengthened linkages between pillars of the Social Protection Strategy and coherence with the Socio-Economic Development Strategy, poverty reduction, labour market and other policy frameworks | FAO ILO, UNDP, UNFPA, UNICEF, UN Women |  |  |  |
|  |  | - Support to the formulation of integrated and evidence-based social protection action plans at national and sub-national level, which take into account emerging vulnerabilities and risks – like climatic and economic shocks – and the changing demographic and socio-economic profile of Viet Nam | ILO, UNDP, UNICEF, UN Women |  |  |  |
| Draft Output 2.1.3: Alternative legal, policy, targeting, and financing options are available and considered by the Government for the expansion of integrated and adequate social assistance, social insurance and social welfare and protection services |  |  |  |  |  |  |
| - Rationale: - These areas were retained as representing critical pillars of the social protection strategy for UN support to focus on. Key actions have a strong focus on the expansion of assistance and insurance policies to enhance people’s protection from shocks and to ensure equal access to opportunities and essential social services, in particular for women and ethnic minorities. The key actions further emphasise the need for a solid legal framework for the protection of children and vulnerable people from abuse, exploitation, violence, and discrimination. The need for these key actions is related to the current lack of capacity of the social protection policies, system and legal framework to help people overcome shocks and deal with vulnerability. Obviously, both social assistance and insurance will need to address new risks, like economic shocks and climate change. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| 2.1.3: Alternative legal, policy, targeting, and financing options are available and considered by the Government for the expansion of integrated and adequate social assistance, social insurance and social welfare and protection services | Indicator 1: Proportion of social protection beneficiaries aware of their entitlements Baseline (2011): Low degree of awareness among social protection beneficiaries on their entitlements Target (2016): 80% of social protection beneficiaries aware of their entitlements MoV: Survey report Indicator 2: Extent to which legal reform recommendations as well as alternative policy options for the expansion of social assistance and social insurance have been discussed in the appropriate fora Baseline (2011): Legal reform and policy options not available 2016 Target: Relevant legal reform recommendations of selected laws, and design, targeting, and financing options in agreed policy areas made available and discussed with policy makers MoV: Study and analysis reports, policy dialogue documentations, legal reform review report | - Support to awareness raising about entitlements to social protection policies | ILO, IOM, UNICEF | MOLISA, MOF, MPI, CEMA, MOH, MOJ, MOCST, relevant NA committees, research institutions, Viet Nam Urban Development Agency, Viet Nam Social Security, VGCL, VCCI, VCA, VAC, MPS, ACVN, selected provinces |  | 10,870,000 |
|  |  | - Support to the design and costing of policy options for the expansion of social assistance and social welfare and protection services | UNICEF, UN-HABITAT |  |  |  |
|  |  | - Support and advocacy for an enhanced and coherent legal framework for the protection of children, migrants, people living with HIV and people living with disabilities | IOM, UNAIDS, UNDP, UNICEF, UN Women |  |  |  |
|  |  | - Support to the design and costing of policy options for the expansion of social insurance (unemployment/crop insurance, pensions) in particular for informal workers, women in particular | FAO, ILO, UN Women |  |  |  |
| Draft Output 2.1.4: Institutional and human resource capacity strengthened to design and deliver social assistance, social insurance, and social welfare and protection services |  |  |  |  |  |  |
| - Rationale: This area of support addresses challenges related to the Implementation and delivery of social protection, with a particular focus on capacity development both at institutional as well as human resource level. The key actions address major identified bottlenecks in the implementation of social protection policies, including the development of the social work profession which cuts across all pillars of the social protection strategy. It further supports the Government in harmonising and implementing relevant national and targeted programmes for particularly vulnerable groups, including the strengthening of child protection systems, access to special protection measures for victims of abuse and exploitation and community-based reintegration and support services for survivors |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| 2.1.4: Institutional and human resource capacity strengthened to design and deliver social assistance, social insurance, and social welfare and protection services | Indicator 1: Level of implementation of the long-term capacity development plan for social workers Baseline: Social work capacity development plan not available 2016 Target: Social work system/ network in place in relevant areas MoV: One Plan annual review reports Indicator 2: Extent to which the system of welfare and protection services, particular child protection is responsive to social protection needs Baseline: Welfare and child protection services are not sufficiently responsive to social protection needs 2016 Target: Relevant agencies are fully equipped with technical capacity in financing and costing social protection interventions and the social welfare services and protection services are responsive to social protection needs MoV: Capacity review reports, documentation of social protection strategy implementation process | - Support to the development of the social work profession | UNICEF | MOLISA, MOF, MPI, CEMA, MOH, WU, MPS, MOET, MOC, MOJ MARD, MOCST, MOFA, ACVN, Viet Nam Urban Forum, Viet Nam Urban Development Agency, VSS, Border guards, PSPMOs (political, social, professional and mass organisations), selected provinces |  | 9,600,000 |
|  |  | - Support to the strengthening of child protection systems and social welfare services, including community based support and care | ILO, IOM, UNICEF, UNODC |  |  |  |
|  |  | - Capacity development for financing & costing of social protection, use of disaggregated data in the formulation of social protection action plans and policies and for the implementation of integrated social protection policies and services | ILO, UNICEF, UN-HABITAT UN Women |  |  |  |
|  |  | - Institutional and human resource capacity development to provide social welfare and protection services to victims of human trafficking with a focus on consistent and comprehensive return and reintegration assistance | IOM, UNESCO, UNICEF |  |  |  |

| Draft Outcome 2.2: By 2016, increased quality and effective management of a comprehensive national health system, including health promotion and health protection, with a focus on ensuring more equitable access for the most vulnerable and disadvantaged groups |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Draft Output 2.2.1: Policy advice and technical support provided to strengthen building blocks of human and animal health systems at national and local levels |  |  |  |  |  |  |  |
| - Rationale: Fundamental to being able to provide health services is the need for effective and efficient systems, for health protection, health promotion and curative diagnostic and treatment services and for animal health services. As such, the health system is much more than the health sector, and it encompasses all sectors that have responsibility for health-related matters and safety (for example, the Ministry of Public Security and Ministry of Transport have responsibilities for road traffic injuries, MOLISA for occupational health, and Ministry of Agriculture and Rural Development (MARD) for animal health). - The focus on strengthening the health system is in response to many sectoral reviews, such as the Joint Annual Health Reviews and in support of the 5 year Health Plan 2011-2015 and strengthening veterinary service delivery in view of PVS report and the gap analysis report including the move towards One Health which can strengthen appropriate linkages between human and animal health sectors. These reviews and plans demonstrate the need for development assistance to strengthen aspects of governance and leadership, such as policy development processes and planning at the sub-national level, to continue to strengthen the coordination between development partners and Government and effectiveness of mechanisms such as the Health Partnership Group. Multiple aspects of health financing are still challenging and development assistance is needed to identify strategies that will ensure greater coverage under health insurance and more effective use of available resources so that the current level of out-of-pocket payments of 56% (2008) will continue to reduce and the poor and vulnerable groups will be protected from potential catastrophic health care costs. This is linked closely to the Government's Social Protection Strategy and the UN Social Protection Floor Initiative. Quality, use and availability of health information and research needs further improvement, and significant challenges remain in the management, distribution, retention and updating of key health personnel and the health training systems. There is a need for greater rationality, cost effective use and more equitable access to medicines, essential health technologies and medical products of assured quality, and for promoting further a primary health approach and strengthening the quality and safety of services and increase responsiveness to service users. Many of these system issues are relevant to both human and animal health systems. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners |  | Assumptions | Indicative Budget (US$) |
| Output 2.2.1: Policy advice and technical support provided to strengthen building blocks of human and animal health systems at national and local levels | Indicator 1: Number of policies commented on or policy options identified, advocated and adapted for strengthening human and animal health systems Baseline (2011): Target (2016): MoV: | - Support the strengthening of health governance and leadership. This Key Action includes health policy development, regulation and enforcement, strategic management and planning, inter-sectoral and inter-institutional coordination, organization of public and non-public services, and strengthening public involvement in processes for policy development, planning, monitoring, review and evaluation (Joint Annual Health Review activities) and service delivery. | FAO, WHO | - MOH (including various institutes), - MARD (including various institutes), - National Assembly, - selected provincial departments of health, various health and medical research and training institutions, PSPMOs |  |  | 21,110,000 |
|  |  | - Improve health financing including social health insurance. This Key Action includes support to strengthen (i) national and local government capacity in evidence-based health financing policy-making, collection and analysis of health financing data, (ii) management of the national health insurance system, and (iii) monitoring the impacts of health financing policies and strategies on equity and access to services particularly for poor and disadvantaged groups. | UNAIDS, UNICEF, WHO | - MOH (including various institutes), - selected provincial departments of health, Viet Nam Social Security, National Assembly, - various health and medical research and training institutions, PSPMOs |  |  |  |
|  |  | - Support improvements in the health information and research systems This includes (i) transparently provide disaggregated data (by sex, ethnicity and socio-economic determinants (wealth, geography, rural/urban, age, etc)), (ii) facilitate the coordination and ethical oversight of research, and (iii) make available high quality, timely, relevant evidence for health policy, planning, management and monitoring that is used by both government and development partners and is accessible by the public. | FAO, UNAIDS, UNFPA, UNICEF, WHO | - MARD, (including various institutes), - MOH (including various institutes), - selected provincial departments of health, various universities, - GSO, VWU |  |  |  |
|  |  | - Support improved human and animal health workforce planning, performance, quality of training, retraining and maintenance of standards, deployment, retention, utilization., and quality of human resource management | FAO, UNFPA, WHO | - MOH (including various institutes), - MARD (including various institutes), - various medical/health and agricultural research and training institutions |  |  |  |
|  |  | - Improve regulation and access to medicines, medical products, devices and technologies. This includes support for developing evidence-based policies for improving equitable access to and cost-effective rational use of medicines, medical products and devices and essential health technologies, and strengthening regulatory and other systems to implement, monitor and enforce internationally accepted standards of safety and quality for medicines, products and technologies | FAO, WHO | - MARD (including various institutes), - MOH (including various institutes), - National Assembly, - various universities, - National Office for Intellectual Property (NOIP) |  |  |  |
|  |  | - Improve the responsiveness of services by strengthening primary health care, improving the quality* of services, and strengthening health promotion and health protection services that address the social, economic and environmental determinants of health particularly for vulnerable populations. - (* Quality in this context includes the acceptability and appropriateness of services from gender, cultural and other perspectives, timeliness, safety, ethical and legal compliance, effectiveness and efficiency) | FAO, IOM, UNFPA WHO | - MARD (including various institutes), - MOH (including various institutes), - selected provincial departments of health and hospitals, - various medical/health and agricultural universities |  |  |  |
| Draft Output 2.2.2: Policy advice and technical support provided to prevent and effectively manage non-communicable conditions* at national and sub-national levels |  |  |  |  |  |  |  |
| Rationale: Non-communicable diseases account for 63% of all deaths in Viet Nam (MOH, 2009). Diabetes prevalence has almost doubled in the period 2002-2008 (now >5%), approximately 120,000 new cases of cancer are identified each year, and levels of cardiovascular diseases are increasing. The significance of mental health disorders is becoming more evident, with small scale surveys estimating the prevalence of mental disorders at 20-30% of the population. In addition, injuries, poisonings and drownings account for a further 22% of deaths, many in younger age-groups. Together these non-communicable 'conditions' (NCCs) significantly impact on society. Effectively dealing with non-communicable conditions requires effective treatment of injuries and diseases when they occur, as well as prevention and reduction of risk factors. Some information on risk factors is available and shows a very high smoking rate of 47% men (2% of women) and 2/3 of non-smoking Vietnamese (including women and children) are exposed to 2nd hand smoke (GATS, 2010). Seventy percent of primary school aged children do not wear motorcycle helmets (HSPH, 2009), and 78% males and 80% of females reported driving/riding after consuming alcohol in some provinces (HSPH, 2008). Environmental and occupational risks are also a concern. Interventions to reduce risk factors are complex and require multi-sectoral actions. There is very little support from other partners on NCCs, despite their increasing importance. The UN is able to provide and draw on substantial technical expertise and normative guidance for (i) improving the surveillance of NCC risk factors, and monitoring trends in prevalence and effectiveness of intervention programmes; (ii) providing advice to strengthen and implement multi-sectoral policies, as well as improve community awareness and knowledge; (iii) strengthen the capacity of services to respond effectively to NCCs as many are chronic in nature and require longer-term support; and (iv) advise on occupational and environmental health issues and risks. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions |  | Indicative Budget (US$) |
| Output 2.2.2: Policy advice and technical support provided to prevent and effectively manage non-communicable conditions* at national and sub-national levels *Note: the term “conditions” is used instead of “diseases” as it encompasses s diseases, injuries, and health conditions related to work and to the environment | Indicator 1: Number of policies commented on or policy options prepared, advocated, and adapted for development of laws, regulations, multi-sectoral policies, strategies and plans on prevention, control and management of non-communicable Baseline (2011): Target (2016): MoV: | - Support both to develop and improve national and sub-national surveillance systems for monitoring trends of non-communicable conditions and effectiveness of intervention programs, as well as to promote research to analyse social, economic, behavioural and political determinants of non-communicable conditions | UNICEF, WHO | - MOH (including various institutes), - National Assembly, GSO, PSPMOs, various medical/health research and training institutions, national and sub-national media |  |  | 15,080,000 |
|  |  | - Support the development and implementation of multi-sectoral policies to reduce the level of exposure of individuals and populations to the common modifiable risk factors for injuries and non-communicable diseases (e.g. tobacco use, unhealthy diet, physical inactivity, and harmful use of alcohol), while at the same time increase the awareness and capacity of individuals and populations to make healthier choices and follow lifestyle patterns that foster good health | UNICEF, WHO | - MOH (including various institutes), MOF, - MOLISA, National Assembly, PSMPOs, national and sub-national media |  |  |  |
|  |  | - Support for developing policies and strengthening institutional capacity to re-orient and improve effectiveness of services for people with non-communicable conditions using a primary health care approach This includes developing evidence based policies, norms, standards, partnerships, guidelines and good practices for cost-effective preventative and curative interventions, capacity building, and by reorienting the health system to focus more on a primary health care approach to enable effective management of diseases of a chronic nature | UNICEF, WHO | - MOH (including various institutes) - NTSC, MOT, MPS, - MOLISA, National Assembly, PSPMOs, national and sub-national media |  |  |  |
|  |  | - Support for documenting and responding to health consequences associated with environmental and occupational risk factors and climate change | FAO, IOM, WHO | - MOH (including various institutes) - MOLISA (including various institutes), - MOC (including various institutes), - MARD (including various institutes), MONRE, National Assembly, PSPMOs, national and sub-national media |  |  |  |
| Draft Output 2.2.3: National and sub-national capacities enhanced to prevent and control communicable diseases of humans and animals |  |  |  |  |  |  |  |
| - Rationale: While curative health always takes precedence, communicable diseases get less attention unless epidemics reach pandemic proportions or threaten socioeconomic development. Communicable diseases are often difficult to contain through curative measures even when therapies exist and therapies do not work in the scale of economy for livestock production. Prevention, preparedness and planning are the three essential components for control and containment of communicable diseases in people and animals. The proposed output with key actions will ensure improved health service delivery including protection of health from the threats of key* communicable diseases in people and animals especially the vulnerable and disadvantaged groups. During the first decade of the 21st century, Vietnam has experienced successive significant threats to public health and economic growth from the international trans-boundary transmission of new infections in animals. Controlling infectious diseases at the animal-human interface is fundamental to eliminating the impact of these diseases on human health and well-being. The proposed key actions will ensure that by improving the veterinary service delivery, such infections are effectively controlled in the animal sector before they could become a threat to public health and food security and with minimum loss of livestock-based livelihood opportunities, a major occupation of rural women. The high profile interrelated epidemics identified in MDG 6, tuberculosis and HIV, remain significant threats to Viet Nam’s economic and social progress, though HIV remains largely contained within the marginalised behavioural risk groups of people who inject drugs, women who sell sex and men who have sex with men. The evidence is that Viet Nam has still not achieved control over either disease and that key populations at higher risk still do not have sufficient access to services. (UNGASS 2010) Sanitation stands out as the most off-track of Vietnam’s MDG (7: Ensure environmental sustainability) targets. “A lack of coordination among the many government agencies involved has resulted in poorly funded and poorly run programmes”. (DFID 2010) *Key communicable diseases can be defined as those that result in significant social and economic cost and require inter-sectoral cooperation and collaboration for their control. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions |  | Indicative Budget (US$) |
| Output 2.2.3: National and sub-national capacities enhanced to prevent and control communicable diseases of humans and animals | Indicator 1: Number of policies commented on, or policy options prepared, advocated for development of policies and guidelines on prevention and management of key communicable diseases of both human and animals Baseline (2011): Target (2016): MoV: | - Provide technical support to establish effective community and hospital-based surveillance systems at all levels for prevention of major communicable diseases | FAO, WHO | - MOH (including various institutes), - MARD (including departments and Institutions involved in the livestock sector), - National Assembly, - selected provincial departments of health, various research and training institutions, - PSPMOs, national and sub-national media |  |  | 34,160,000 |
|  |  | - Provide technical support to develop evidence based policies, norms, standards, partnerships and guidelines to strengthen prevention and management of communicable disease in humans and animals. | FAO, WHO | - MOH (including various institutes), - MARD (DAH, DLP, NIAH, IPSARD), National Assembly, selected provincial departments of health, various universities, - PSPMOs, national and sub-national media |  |  |  |
|  |  | - Provide technical support to improve health service delivery including immunization and treatment of communicable diseases, through quality assurance and prudent use of vaccines and pharmaceuticals in humans and animals. | FAO, IOM, WHO | - MOH (including various institutes), MARD (DAH, NIVR), National Assembly, selected provincial departments of health, various universities, PSPMOs, national and sub-national media |  |  |  |
|  |  | - Provide technical support to enhance disease diagnostic capacity particularly that of unusual disease events and enhance risk assessment and risk communication capacity | FAO, WHO | - MOH (including various institutes), - MARD (DAH, NIVR), National Assembly, - selected provincial departments of health, various universities, - PSPMOs, national and sub-national media |  |  |  |
|  |  | - Provide technical support to increase awareness, behaviour and practice on communicable disease prevention and management for individuals, families and communities | FAO, IOM, WHO | - MOH (including various institutes), - MARD (DAH, DLP, NAFEC), - National Assembly, - selected provincial departments of health, hospitals, various universities, PSPMOs, national and sub-national media |  |  |  |
|  |  | - Provide technical support for improving safe food production practices including processing and marketing of food that meet national food safety standards in order to prevent and control food-borne diseases | FAO, WHO | - MOH, - selected provincial DOH, - MARD, - Ministry of Commerce and Industry |  |  |  |
| Draft Output 2.2.4: National and sub-national capacities enhanced for universal access to and utilization of a quality package of nutrition and sexual, reproductive, adolescent, maternal, neonatal, and child health care and services |  |  |  |  |  |  |  |
| - Rationale: - Key issues in nutrition and sexual, reproductive, maternal, neonatal, child and adolescent health include significant differences between regions and in minority ethnic groups in terms of maternal, newborn, infant and under-five mortality and stunting rate (29%). Newborn mortality is now half of the under-five mortality and key killers of birth asphyxia, premature/low birth weight and newborn infections have not been significantly reduced. Home deliveries are particularly prevalent in mountainous provinces, and the majority are not supported by a health provider. Only about one third of pregnant women are tested for HIV, and less than one half of those who are HIV-positive receive anti-retrovirals which can prevent mother-to-child HIV transmission. Health issues and problems are also evident in the teenage population with an increased proportion of young migrants, earlier teenage premarital and unprotected sex, and 30% of total abortions occurring among young women (suggesting significantly low contraceptive access and use by adolescents). There are significant shortages of health providers particularly specialists in obstetrics and paediatrics, working in difficult conditions (distances, poor transport, low salaries), and these shortages are worst at lower levels in the health system. A lack of training opportunities and weak supervision have impacted negatively on health provider performance. Poor community knowledge and practices in newborn and child care (for example, only 19% of infants are exclusively breastfeed), difficulties accessing services when needed, and poor referral systems also create problems. The focus on sexual, reproductive, maternal and child health and nutrition is in response to country needs identified in many studies and reviews. It is also in line with national and sub-national priorities outlined in the 5 year health plan of the Ministry of Health 2011-2015 and directions and priorities of the National Population and Reproductive Health Strategy 2011-2010 and the National Nutrition Strategy. This output supports the government to achieve objectives and targets of MDGs 4, 5 and 6 with a strong focus on disadvantaged and vulnerable populations. The UN aims to continue working with the Government, to provide substantial technical expertise, appropriately utilizing international evidence and guidance, to develop relevant country-specific and sub-national policies and guidelines and build capacity in order to increase progress in these critical areas. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners |  | Assumptions | Indicative Budget (US$) |
| Output 2.2.4: National and sub-national capacities enhanced for universal access to and utilization of a quality package of nutrition and sexual, reproductive, adolescent, maternal, neonatal, and child health care and services | Indicator 1: Number of policy commented on or policy options on increasing access to and utilization of sexual, reproductive, adolescent, maternal and child health and nutrition identified and adapted for national implementation. Baseline (2011): Target (2016): MoV: MOH reports, research reports *It assumes that the UN will jointly deliver RH/MCH programme to strengthen capacities of sub-national institutions on universal access to and utilization of MNCH/SRH services | - Support national and sub-national institutions to generate evidence from targeted operations research on universal access to and utilization of quality, gender sensitive sexual, reproductive, adolescent, maternal and child health and nutrition services. | UNFPA, UNICEF, UNODC, WHO | MOH (including various departments and institutions), selected provincial departments of health, MOLISA (including various departments), MARD (including various department and institutions), Ministry of Trade and Industry, National Assembly, Medical and Health Research and Training Institutions, PSPMOs |  |  | - 31,300,000 |
|  |  | 2. Support national and sub-national institutions to use evidence in policy and strategy dialogue and engage communities for improving the development, implementation and monitoring of sexual, reproductive, adolescent, maternal and child health (including immunization) and nutrition policies, laws, and programmes. * This Key Action is linked with Education’s Output 2.3.4 (SRH/HIV counselling integrated into vocational training with ILO (partner MOLISA) and focal education with UNESCO (partner MOET) | UNAIDS, UNFPA, UNICEF, UNODC, WHO | MOH (including various departments and institutions), selected provincial departments of health, MOLISA (including various departments), MARD (including various department and institutions), Ministry of Trade and Industry, National Assembly, Medical and Health Research and Training Institutions PSPMOs |  |  |  |
|  |  | 3. Support improved access to and utilization of quality SRHMNCH services. This Key Action includes (i) strengthening capacity of sub-national institutions to deliver and monitor community-based and institutional programmes, including in difficult-to-reach provinces, and (ii) increasing demand for and awareness of preventive and curative services. | UNFPA, UNICEF, WHO | MOH (including various departments and institutions), selected provincial departments of health, PSPMOs |  |  |  |
| Draft Output 2.2.5: Enhanced national and sub-national capacities to improve equitable access to and demand for quality and sustainable water supply and hygienic sanitation |  |  |  |  |  |  |  |
| - Rationale: - The only MDG that Viet Nam is not currently on track to meet is MDG 7. Target 7c is Reduce by half the proportion of people without sustainable access to safe drinking water and basic sanitation (Targets include the proportion of population using an improved drinking water source and Proportion of population using an improved sanitation facility) In 2007, only 18% of rural households, 12 per cent of rural schools and 37 per cent of Commune Health Stations had hygienic latrines meeting MOH standards. 30% of rural households in Viet Nam use human faeces for cultivating and feeding fish and most households fail to decompose faeces. Almost 50% of all children do not have access to a hygienic sanitation facility in their home. These issues are interrelated with child nutrition and child poverty rates. Access to hygienic water sources and adequate sanitation can have a massive impact on child nutrition status, anaemia rates, worm loads and diarrhoea mortality and morbidity. One of the most cost effective ways in which faecal oral disease spread can be contained is through simple hand washing. Unfortunately in 2007 only 2% of the rural populations were aware that hand-washing with soap is essential to help prevent infectious diseases and only 12% of the rural population washes their hands with soap before eating and only 16% after defecation. Although not publicly acknowledged, cholera outbreaks are ongoing in 20 provinces, with farmers and rural populations most at risk. The combination of hand washing with soaps, improved sanitation and improved water quality at point of use provide the most cost effective and comprehensive way of reducing diarrhoea morbidity. A large degree of inequity is noted between ethnic groups and geographic localities. Emerging inequities and specific issues are occurring in urban contexts which has a specific set of coordination issues. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners |  | Assumptions | Indicative Budget (US$) |
| Output 2.2.5: Enhanced national and sub-national capacities to improve equitable access to and demand for quality and sustainable water supply and hygienic sanitation | Indicator 1: Number of policy commented on or policy options on WASH and interactions with other sectors (e.g. health and education) Baseline (2011): Target (2016): MoV: | - Support to national and sub-national institutions and communities to develop and implement pro poor water and sanitation initiatives and policies reducing gender, geographic and ethnic disparities in access to quality water and sanitation | UN-HABITAT, UNICEF, WHO | - Viet Nam Health Environment Management Agency (VIHEMA), - MOH (including various departments and institutions), MARD (including various departments and institutions), - MOC (including various departments and institutions), - National Centre for clean rural water supply and environment sanitation (NCERWASS), - MOET (including various departments and institutions), - Mekong River Commission (MRC) and Gender & Water Alliance (GWA), - Vietnam Water Supply and Sewerage Association (VWSA), PSPMOs, Research and Training Institutions |  |  | 9,290,000 |
|  |  | 2. Support to national and sub-national institutions and communities to increase awareness of and demand for quality water and sanitation services, including decentralized wastewater treatment and community based solid waste management initiatives | - UN-HABITAT, UNICEF, WHO | - Viet Nam Health Environment Management Agency (VIHEMA), MOH (including various departments and institutions), MARD (including various departments and institutions), - MOC (including various departments and institutions), - National Centre for clean rural water supply and environment sanitation (NCERWASS), - MOET (including various departments and institutions), - Mekong River Commission (MRC) and Gender & Water Alliance (GWA), Viet Nam Water Supply and Sewerage Association (VWSA), - PSPMOs, Research and Training Institutions |  |  |  |
|  |  | 3. Support to implement water safety plan in both urban and rural sectors develop and maintain national monitoring and evaluation systems for trends of access to quality sanitation and water, using best practice research and evidence to guide storage, analysis and dissemination of key data. | - UN-HABITAT, UNICEF, WHO | - Viet Nam Health Environment Management Agency (VIHEMA), MOH (including various departments and institutions), MARD (including various departments and institutions), - MOC (including various departments and institutions), - National Centre for clean rural water supply and environment sanitation (NCERWASS), - MOET (including various departments and institutions), - Mekong River Commission (MRC) and Gender & Water Alliance (GWA), Viet Nam Water Supply and Sewerage Association (VWSA), PSPMOs, Research and Training Institutions |  |  |  |

| Draft Outcome 2.3: By 2016, increased quality and effective management of education and training systems, and increased access to pre-primary, primary and non-formal education, particularly for the most vulnerable and disadvantaged groups |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 2.3.1: High-quality and disaggregated data are available to ensure education policies are inclusive, relevant and learner-friendly with a special focus on vulnerable and disadvantaged groups |  |  |  |  |  |  |
| - Rationale: - There is a need to increase opportunities for equal access to quality education at all levels, especially for vulnerable and disadvantaged groups, particularly girls. The Government of Viet Nam is strongly committed to achieving the EFA objectives and has made significant progress during the last decade. MOET reports the achievement of 96% net enrolment in primary education in 2006-2007. It is widely recognized that access has impressively improved for all groups. However structural challenges remain to reach the remaining 4%, the majority of whom are poor, disadvantaged and from ethnic minorities. As the pace of development in remote areas is slower than in urban environments, disparities between regions are growing. The difference in quality of education is likely to increase, especially for ethnic minorities in geographically isolated areas and for children living in areas affected increasingly by natural disasters resulting from effects of climate change. As an effect of these challenges, many boys and girls drop out/ leave school early which limits their potential and has a negative impact on families, communities and the wider socio-economic development of the country as a whole. Due to urbanization and migration as well as climatic stresses, new marginalized groups of children will require support to ensure access to quality education as well. In terms of policy monitoring the focus will be on the Law and Decree on People with Disabilities (education component) and development of related circulars, the National Plan of Action on Children affected by HIV and AIDS, the Socialisation Policy, EDSP 2011-2020, the EFA National Plan of Action etc). Similarly the UN will support development of policies in the areas of education in emergencies, climate change and education, ethnic minority human resource development, Bilingual Education, Lifelong Learning, etc. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 2.3.1: High-quality and disaggregated data are available to ensure education policies are inclusive, relevant and learner-friendly with a special focus on vulnerable and disadvantaged groups. | Indicator 1: Number of studies on inclusive learner friendly educational approaches targeting disadvantaged learners including ethnic minorities conducted and disseminated Baseline (2011): 0 Target (2016): 5 MoV: Indicator 2: Number of Government officials, policymakers and stakeholders with increased understanding on barriers on education for ethnic minority children (through participation in dissemination events and workshops). Baseline (2011): 100 Target (2016): 300 MoV: | - Support systematic generation of data and information for evidence based monitoring of the implementation of inclusive, relevant, learner-friendly educational policies at national and sub-national levels, in particular for improved access to education for ethnic minority learners especially girls, disadvantaged groups and those affected by climate change | UNESCO, UNICEF | MOET, National Assembly, Community Party, Committee for Ethnic Minorities, donors, media, teachers, local authorities, PSPMOs |  | 7,750,000 |
|  |  | - Strengthen evidence based advocacy to line ministries (MOET, MOLISA), central ministries (MPI, MOFA), the National Assembly and Communist Party for inclusive education policies that support the most vulnerable and disadvantaged, in particular for bilingual education for ethnic minority learners and girls | - UNESCO, UNICEF | MOET, National Assembly, Community Party, Committee for Ethnic Minorities, donors, media, teachers, local authorities, PSPMOs |  |  |
| Draft Output 2.3.2: - MOET has enhanced capacities to improve learning outcomes and literacy for vulnerable and disadvantaged groups |  |  |  |  |  |  |
| - Rationale: - Assure improvement in education quality to meet the international standards and national goals. Significant challenges in terms of education quality are recognised by key policy documents such as the SEDP as well as the EDSP drafts, demonstrating MOET’s commitment to address the challenging issues regarding quality of education. There are growing concerns about the mismatch between theory and practice in the curriculum and the perceived irrelevance of some of the curriculum content. For students whose mother tongue is not Vietnamese, the language barrier is one of the key obstacles to both accessing education and ensuring the quality of learning. Based on continued efforts to update teaching and learning methodologies, good practices of interactive learning in the class room, and for development of students’ life skills are now expected to be disseminated nationwide to replace the still common lecture-based approach. Furthermore, there is a need to integrate issues relevant to young people into the curriculum, including climate change and environmental sustainability, cultural diversity, reproductive health, HIV prevention and life skills. To further strengthen the evidence base for the improved quality of learning and literacy, there is a need for a comprehensive national assessment framework based on international instruments such as PISA and LAMP which Viet Nam will be implementing during the period 2011-2015. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 2.3.2: MOET has enhanced capacities to improve learning outcomes and literacy for vulnerable and disadvantaged groups | Indicator 1: Number of curriculum experts trained on tools and guides to integrate environmental sustainability, cultural diversity, reproductive health, HIV prevention and relevant life skills into the curriculum Baseline (2011): 0 Target (2016): 100 MoV: Indicator 2: Number of education managers trained on the use of learning outcome assessment tools and instruments for improved planning and monitoring Baseline (2011): 0 Target (2016): 100 MoV: | - Support curriculum innovation and development for integration of environmental sustainability, cultural diversity, reproductive health, HIV prevention and relevant life skills for learners from vulnerable and disadvantaged groups, adolescents and youth | UNESCO, UNFPA | - MOET, MOLISA, MOCST |  | 5,500,000 |
|  |  | - Strengthen MOET capacities to further improve teachers’ pedagogical skills and capacities to deliver more inclusive and learner-friendly education and life skills including addressing sensitive issues of sexuality education, reproductive health and HIV prevention. | - UNESCO, UNFPA | MOET, MOCST, TTIs |  |  |
|  |  | - Support implementation of MOET’s priorities in literacy strategy, including literacy assessment, review of national literacy standards to better address literacy needs of vulnerable and disadvantaged groups | - UNESCO | MOET, GSO |  |  |
|  |  | - Strengthen institutional capacities at national and sub-national level to use evidence from the assessments of literacy and learning outcome for improved and more inclusive learning opportunities of vulnerable and disadvantaged groups | - UNESCO, UNICEF | MOET, GSO, MOLISA, international multilateral and bilateral organisations |  |  |
| Draft Output 2.3.3: Education institutions and managers at national and sub-national levels have enhanced capacities to develop, implement and monitor evidence based policies and programmes for improved quality of teaching and learning for all |  |  |  |  |  |  |
| - Rationale: Further strengthen education management systems at all levels to deliver quality education for all. An effective and evidence-based education management system is critical in order to address the issues of access, equity and quality at all levels of education. This requires data that is updated and disaggregated by sex and ethnicity as well as continuous development of capacities for educational planning, financing and budgeting, especially in the context of decentralised planning and management. Also there is a need to close the gap between innovations introduced through policy and real changes at implementation level in order to monitor and assure system-wide quality. Further, with Viet Nam's entry to WTO, a large number of private and foreign education institutions are entering Vietnam particularly at higher education level, which requires effective quality assurances and accreditation (QAA) mechanisms to ensure that students benefit from higher education of highest quality. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 2.3.3: Education institutions and managers at national and sub-national levels have enhanced capacities to develop, implement and monitor evidence based policies and programmes for improved quality of teaching and learning for all. | Indicator 1: Number of provinces undertaking regular and systematic monitoring of the implementation of education policies for disadvantaged children Baseline (2011): 0 Target (2016): 7 MoV: Indicator 2: Number of QAA Agencies established Baseline (2011): 0 Target (2016): 1 MoV: | - Strengthen capacities of education managers at the national and sub-national levels to rights-based and evidence based education planning to ensure equity in formal education, particularly for learners from vulnerable and disadvantaged groups. | UNESCO, UNICEF | MOET, main partner: Provincial Department of Education and Training in selected provinces. Other partners: MOET, PPC, DPI and other relevant Departments in selected provinces |  | 4,900,000 |
|  |  | - Strengthen MOET capacities for ensuring effective quality assurance and accreditation (QAA) of national education system, particularly at the higher education | UNESCO | - MOET, Higher Education Institutions |  |  |
| Draft Output 2.3.4: - Government and the private sector institutions have enhanced capacities to integrate a life skills approach into technical and vocational education and training programmes at non-formal, lower-secondary, secondary and tertiary education levels |  |  |  |  |  |  |
| Rationale: - The draft SEDP 2011-2015 includes education and skills development as one of the priorities, recognizes improvements in the quality of education and training, but acknowledges that the quality is still low relative to the requirements for Vietnam’s continued development. While it is estimated that the higher education system absorbs fewer than 3 out of 10 university applicants, the issue of university graduates being unable to secure employment in their fields of specialization still remains. The Government of Viet Nam has acknowledged the importance of ensuring demand driven training and equipping young people with necessary life skills. Hence, there is an opportunity to address the special needs of young learners on health, life skills including sexual and reproductive health and HIV protection in the technical and vocational training programmes. This requires significant improvements in the technical and vocational education and training at lower-secondary, secondary and tertiary levels of education to prepare school graduates for school to work transition as well as to cope effectively with health risks, especially sexual and reproductive health. There is an opportunity for effective cooperation between enterprises, training institutions and the Government for achieving demand driven training. UN support to encourage better communication and collaboration amongst these three sets of actors and industry participation on effective monitoring implementation of education and training programmes that are relevant and responsive to the needs of the learners and the economy. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 2.3.4: Government and the private sector institutions have enhanced capacities to integrate a life skills approach into technical and vocational education and training programmes at non-formal, lower-secondary, secondary and tertiary education levels | Indicator 1: A proposed M&E framework for monitoring implementation of TVET programmes in formal and non-formal education Baseline (2011): 0 Target (2016): 1 MoV: Indicator 2: Life skills, career counseling and guidance system for lower-secondary and secondary learners Baseline (2011): 0 Target (2016): 1 MoV: | - Support strengthening of MOLISA, MOET and the private sector to monitor implementation of evidence based technical, vocational and professional development programs. | ILO, UNESCO | MOET, MOLISA, Provincial DOETs, DOLISA PPCs, VCCI, MOH, Viet Nam Youth Association |  | 1,600,000 |
|  |  | - Support elaboration of workplace professional development and non-formal TVET programmes within the framework of lifelong learning. | - ILO, UNESCO | - MOET, MOLISA, MPI, MOFA, Provincial DOETs, DOLISA PPCs, VCCI, MOH, Viet Nam Youth Association |  |  |
|  |  | - Support development of counseling systems for career guidance, life skills including sexual and reproductive health, HIV protection for young learners of technical and vocational training programmes | - ILO, UNESCO, UNFPA | MOET, MOLISA, MOH VCCI, MOH, Viet Nam Youth Association |  |  |

| Draft Outcome 2.4: By 2016, national and sub-national institutions, in partnership with communities, more actively address inequalities through implementation and monitoring of laws, policies and programmes that promote gender equality and women’s empowerment, and an effective and sustainable response to HIV, reducing stigma and discrimination |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 2.4.1: National HIV legal and policy frameworks strengthened to guide evidence-informed responses that effectively address stigma, discrimination, inequality and inequity |  |  |  |  |  |  |
| - Rationale: The inconsistent policy and regulatory documents, weak implementation of the 2006 Law on HIV coupled with stigma and discrimination against PLHIV and key affected populations hampers access to prevention, treatment, care and support services. The government will need technical support for the realization and monitoring of the newly developed National strategies on HIV 2011-2020. Gaps exist in the implementation of evidence-informed HIV interventions targeting key populations at higher risk, as well as lack of national HIV research and evaluation agenda. There are no specific behavioural studies among young people at higher HIV risk, which could potentially flag the emerging risk profiles. Gender considerations and analysis in HIV response has been limited, there is also a gap in knowledge and analysis of how HIV is related to and affects poverty, ethnicity and migration. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 2.4.1: National HIV legal and policy frameworks strengthened to guide evidence-informed responses that effectively address stigma, discrimination, inequality, and inequity | Indicator 1: Number of policy advice papers covering HIV related: (a) stigma and discrimination; (b) inequality; and (c) inequity prepared and submitted for consideration to GoV Baseline (2011): 0 Target (2016): 10 MoV: One Plan Annual Reports Indicator 2: Number of UNGASS progress reports developed through a consultative process with PSPMOs Baseline (2011): 0 - Target (2016): 3 MoV: One Plan Annual Reports | - Support relevant ministries and other key stakeholders in the development and revision of effective HIV, drugs and sex work legal and policy frameworks and strategies, including the sharing of international experiences in policy dialogue and development | ILO, IOM, UNAIDS, UNFPA, UNDOC, UN Women, WHO | National Committee on AIDS, Drugs and Prostitution Prevention and Control; People’s Committees; MOH, MOLISA, MOPS, MoCST, MOET, National Assembly, PSPMOs, various health and medical universities and research institutions |  | - 8,510,000 |
|  |  | - Support relevant ministries ,the media and other key stakeholders to implement HIV, drugs and sex work legal and policy frameworks and strategies, including awareness raising among duty bearers and the rights holders, and targeted support to populations at higher risk including sex workers, MSM, and IDUs, PLHIV, and people affected by HIV to reduce stigma, discrimination, inequalities and inequity. | ILO, IOM, UNAIDS, UNESCO, UNFPA, UNODC, UNV, UN Women, WHO | National Committee on AIDS, Drugs and Prostitution Prevention and Control, National Assembly, various health and medical universities and research institutions, MOH, MOLISA, MOPS, MoCST, MOET, PSPMOs |  |  |
|  |  | - 3.Support relevant ministries and other key stakeholders to strengthen linkages between HIV , social, SRH and other health services, at the national and sub-national levels, to provide the universal access to HIV prevention treatment, care, and support | ILO, IOM, UNAIDS, UNFPA, UNODC, UNV, WHO | MOH, MOLISA MOPS, MoCST, MOET, National Assembly, PSPMOs, various health and medical universities and research institutions |  |  |
|  |  | - 4. Technical support to relevant ministries and key stakeholders to strengthen HIV related and M&E coordination, capacity building and research, and facilitate review, harmonisation, and linkages of the HIV M&E systems | UNAIDS, UNESCO, UNFPA, UNODC, WHO | MOPS, MOH, VAAC, MOET, MOLISA, National Asembly, various health and medical universities and research institutions, Groups of PLHIV, PSPMOs |  |  |
|  |  | - 5.Strengthen capacity of line-ministries and other key stakeholders on HIV analysis, and data use, to monitor and inform policy formulation and implementation, and report against the HIV Declaration of Commitment, Universal Access and Millennium Development Goals | ILO, UNAIDS, UNESCO, UNFPA, UNODC, UN Women, WHO | MOCST, MOLISA, NCFAW, MOHA, MOF, MPI, MOH, GSO, NCCP, MOPS, MOET, MOH, VAAC, MOET, Groups of PLHIV, PSPMOs, VWUN, VCCI, VASS |  |  |
| Draft Output 2.4.2: Multi-sectoral coordination mechanisms are strengthened to ensure full engagement and participation of key stakeholders to support a sustainable HIV response |  |  |  |  |  |  |
| - Rationale: HIV multi-sectoral policy coordination is inadequate, and the government HIV budget is limited and poorly allocated. There is a lack of coordination and coherence in the strategies and plans developed by different ministries, with dominance of project modalities and limited engagement of political, social, professional and mass organisations (PSPMOs), and the private sector. The diminishing donor funding should be turned into an opportunity to consider a more efficient, locally owned and sustainable response. Human resource capacity for HIV requires further development and strong systems are essential to achieve universal access to HIV prevention, treatment and care services. Greater human and financial investment is required to achieve the MDGs for all Vietnamese people, including targets where Viet Nam is currently lagging behind such as Goal 6 on HIV. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 2.4.2: Multi-sectoral coordination mechanisms are strengthened to ensure full engagement and participation of key stakeholders to support a sustainable HIV response | Indicator 1: - Number of scenarios for a sustainable financial HIV response developed Baseline (2011): 0 Target (2016): 3 MoV: One Plan Annual Reports - Indicator 2: Number of PLHIV and Key Affected Population (KAP) members of the HIV multi-sectoral Coordination mechanisms Baseline (2011): 2 Target (2016): 6 MoV: List of Members of the National Committee, CCM | - Advocate to and support the National Committee on AIDS, Drugs and Prostitution Prevention and Control, the Parliamentary Committee for Social Affairs (PCSA) and relevant line ministries for a multi-sectoral approach in HIV programming and, resource mobilization. | IOM, UNAIDS, UNESCO, UNFPA, UNODC, WHO | National Committee on AIDS, Drugs and Prostitution Prevention and Control, National Assembly Committee for Social Affairs , MOH, VAAC MOLISA, MOPS, MoCST, MoF, MOET, various health and medical universities and research institutions, PSPMOs |  | - 3,030,000 |
|  |  | - Support the National Committee on AIDS, Drugs and Prostitution Prevention and Control and relevant ministries in developing approaches for a sustainable financial HIV response | - UNAIDS, UNFPA, UNODC, WHO | National Committee on AIDS, Drugs and Prostitution Prevention and Control, National Assembly Committee for Social Affairs, MOH, MOLISA, MOPS, MoCST, MoF, MOET |  |  |
|  |  | - Groups of PLHIV and key populations at higher risk for HIV infection supported to represent their constituencies and more effectively participate in the planning, implementation, monitoring and evaluation of a gender-sensitive, human-rights-based and sustainable response to HIV. | - UNAIDS, UNFPA, UNODC, UNV, UN Women, WHO | Groups of PLHIV, PSPMOs MOH, MOLISA, National Assembly, various health and medical universities and research institutions |  |  |
|  |  | - International support to the national HIV response coordinated through the HIV Technical Working Group, the HIV Ambassadors and Heads of Agency Group, One UN and other fora and mechanisms. | - ILO, UNAIDS, UNESCO, UNFPA, UNICEF, UNODC, UN Women, WHO | - National Committee on AIDS, Drugs and Prostitution Prevention and Control, MOH, PSPMOs, - HIV TWG and Ambassadors group, HOAs group - MOLISA, MOH - National Assembly, various health and medical universities, research institutions |  |  |
|  |  | - Build the capacities of members of the National Committee on AIDS, Drugs and Prostitution Prevention and Control, including relevant ministries and other institutions, as well as key populations at higher risk for HIV infection , PLHIV and people affected by HIV, to address HIV related inequalities and inequity in programmes and services and achieve Universal Access | ILO, UNAIDS, UNFPA, UNODC, UN Women, WHO | National Committee on AIDS, Drugs and Prostitution Prevention and Control, MOPS, MoCST, MOH, MOLISA, PSPMOs |  |  |
| Draft Output 2.4.3: Gender related legal and policy frameworks, programmes and practices effectively address gender inequality and inequity, gender discrimination and gender-based violence |  |  |  |  |  |  |
| - Rationale: Gender-based violence (GBV), especially violence against women and girls, is a serious problem globally including in Viet Nam, as shown by available data. Many women and girls are subject to domestic violence, exploitation, sexual violence, and other forms of violence against their bodies, minds and human dignity. GBV is a symptomatic deep-rooted gender inequality that is present in most societies. It is a health, legal, socio-economic, education issue, and a violation of human rights. Viet Nam has legal and policy frameworks in place to address violence, especially domestic violence as enshrined in the 2007 Law on Domestic Violence Prevention and Control and subsequent legal and policy documents. However, challenges exist in relation to implementation, availability of services and support, protection, and coordination mechanisms across government and service providers. There is a significant need for a comprehensive, systematic, and human-rights based national response to GBV in Viet Nam targeting duty bearers, perpetrators, survivors, and the public. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| - Output 2.4.3: Gender related legal and policy frameworks, programmes and practices effectively address gender inequality and inequity, gender discrimination and gender-based violence | Indicator 1: Number of policy advice papers covering: (a) gender equality and inequity, (b) gender-based violence prepared and submitted for consideration to GoV Baseline (2011): Target (2016): MoV: Indicator 2: Availability of minimum comprehensive GBV package Baseline (2011): 0 Target (2016): 1 MoV: | - Support relevant ministries and other key stakeholders in formulating, implementing, & monitoring gender related laws, policies and strategies, in particular the NSGE and NPGE and gender mainstreaming regulations (including advocacy, communication and data analysis) | ILO, UNAIDS, UNESCO, UNFPA, UNODC, UNV, UN Women | - MOET, MOLISA, MOCST, MOH, MOHA, MPI, MOJ, MPS, MOIC, SPC, SPP, NA, VWU, VCCI, VCA, VGCL, media, PSPMOs |  | 8,190,000 |
|  |  | - Support relevant ministries and other key stakeholders in formulating and implementing a legal and policy framework related to imbalanced sex-ratio at birth | UNFPA | - MOH, GOPFP, MOCST, MOLISA, MOET, SPC, SPP, selected provinces, PSPMOs, media |  |  |
|  |  | - Support relevant ministries and other key stakeholders in developing a comprehensive legal, policy and service framework to address Gender-Based Violence, and in implementing existing related policies, laws, and strategies | ILO, UNFPA, UNICEF, UNODC | MOCST, MOLISA, MOH, MOJ, MOET, MPS, SPC, SPP, selected provinces, PSPMOs, media |  |  |
|  |  | - Strengthen capacity of central and local authorities and other key stakeholders to promote GE, women’s empowerment, and GBV prevention in partnership with communities | IOM, UNFPA, UNODC, UNV | MOCST, MOLISA, NCFAW, MOH, GSO, MOJ, MPS, MOET, SPC, SPP, selected Provinces, PSPMOs, media |  |  |
|  |  | - Support relevant ministries and other key stakeholders to strengthen capacities of national, provincial, and local institutions involved in development and implementation of GE, including GBV and SRB related policy and legal framework | UNFPA, UNODC, UN Women, WHO | MOCST, MOLISA, NCFAW, MOH, GSO, NCCP, MPI, MPS, MOJ, SPC, SPP, selected provinces, PSPMOs |  |  |
| Draft Output 2.4.4: Multi-sectoral coordination mechanisms effectively guide comprehensive evidence-based planning, budgeting, M&E for a sustainable response to gender inequality, inequity, discrimination and gender-based violence |  |  |  |  |  |  |
| - Rationale: The Law on Gender Equality and Law on Domestic Violence Prevention and Control have supported efforts to create a legal and policy framework that addresses gender-based violence. Major challenges to policy implementation include insufficient coordination, financial resources, human resource capacity and strategic monitoring of programme investments to ensure desired results are achieved. Currently, there is not a national multi-sectoral GBV prevention and response planning, monitoring and evaluation framework (PM&E) that harmonizes all relevant ministerial and related agencies, and data collection systems to include monitoring for GBV. In addition, a national multi-sectoral coordination mechanism to guide a national GBV framework is not available. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| - Output 2.4.4: Multi-sectoral coordination mechanisms effectively guide comprehensive evidence-based planning, budgeting, M&E for a sustainable response to gender inequality, inequity, discrimination and gender-based violence | Indicator 1: Availability of a national planning and M&E Framework on gender-based violence as part of the multi-sectoral coordination mechanism Baseline (2011): 0 Target (2016): 1 MoV: Indicator 2: Evidence of strengthened Gender Action Partnership mechanism through documentation of frequency of meetings, agendas and attendance Baseline (2011): Target (2016): MoV: | - Advocate to and support relevant ministries and other key stakeholders to strengthen multi-sectoral coordination mechanism for gender equality, | - IOM, UNFPA, UNODC, UN Women | - MOCST, MOLISA, MOH, MPS, MOJ, GSO, SPC, SPP, selected provinces, PSPMOs, media |  | 2,590,000 |
|  |  | - Support relevant ministries and other key stakeholders to develop a multi-sectoral coordination mechanism for gender based violence prevention and response including domestic violence at national and sub-national levels | - UNFPA, UNV | - MOET, MOH, MPS, MOJ, GSO, SPC, SPP, selected provinces, PSPMOs, media |  |  |
|  |  | - Technical support to relevant ministries and key stakeholders to develop and implement comprehensive Planning and M&E Frameworks on Gender Equality and GBV | - ILO, UNFPA, UNODC, UNV, - UN Women | - MOET, MOH, MPS, MOJ, GSO, SPC, SPP, selected provinces, PSPMOs, media |  |  |

UN Focus Area 3: Governance and Participation

| Draft Outcome 3.1: By 2016, elected bodies are better able to formulate laws and oversee the performance of state agencies and represent the aspirations of the Vietnamese people, especially women, ethnic minorities and other vulnerable and disadvantaged groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Draft Output 3.1.1: Elected bodies have access to high quality research and data to guide their legislative duties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Rationale: Viet Nam is committed to further institutional reforms, which are needed to keep pace with its continued socio-economic development. As the country takes up middle-income status, addressing gaps in requirements for inclusive decision-making, accountability, transparency and efficiency becomes more critical for the sustainability of the reform and development process. To perform their key functions, elected bodies will require increased capacity for analysis and monitoring of policies and laws, enhanced knowledge of international conventions and norms including a rights-based and culturally sensitive approach. With comparative advantages in policy advice, the UN will support the strengthening of law-making and oversight functions performed by elected officials and committees through capacity development and policy work to reflect an evidence-based, gender equitable, rights-based and culturally sensitive approach. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators |  | Draft Key Actions |  |  | UN Agencies |  |  | Partners |  |  | Assumptions |  |  | Indicative Budget (US$) |
| Output 3.1.1: Elected bodies have access to high quality research and data to guide their legislative duties | Indicator 1: Extent to which relevant research findings have been discussed and considered for use by elected bodies in adoption of laws, ordinances and development of oversight guidelines and tools Baseline (2011): limited existence and use of research findings Target (2012): Relevant research findings are used by elected bodies in adoption of all laws, ordinances and development of oversight guidelines and tools MoV: Indicator 2: Number of guidelines and tools incorporating cross-cutting issues of RBM, gender, culture, and rights of all vulnerable groups are available to be use by elected bodies in oversight of policy implementation Baseline (2011): no baseline data available Target (2016): 100% of law/ordinances developed with UN support are provided with reference documents MoV: IPs quarterly and annual reports |  | - Support to conduct and disseminate assessments, research/studies to have evidence accessed and considered by elected bodies so that they can be used to guide the development and implementation of laws, procedures, guidelines and tools for oversight |  |  | ILO, UNDP, UNFPA, UN-HABITAT, UNICEF |  |  | 1. NA Committees (Committee of Culture, Education, Youth and Children, Committee of Social Affairs, Judicial Committee, Ethnicity Council), Office of NA, Institute for Legislative Studies, Training Center for Elected Representatives) 2. Party Commissions (CPV’s Central Commission for Popularization and Education), Research Institute of Human Rights of HCM National Political and Administrative Academy) 3. Selected Local People’s Councils, 4. MOJ, CEMA, VASS, AMCC |  |  |  |  |  | 7,350,000 |
|  |  |  | - Support to the development of tools and guidelines to be used by elected bodies for oversight |  |  | - UNDP, UNESCO, UNFPA, UN-HABITAT, UNICEF, UN Women |  |  | - NA, CEMA, VASS, - NA (Committee of Culture, Education, Youth and Children; Committee of Social Affairs, Judicial Committee, Committee, Ethnicity Council), ONA, Training Center for Elected Representatives, Institute of Legislative Studies and selected People's Councils, - Institute for Human Rights Studies/ Ho Chi Minh National Political Administrative Academy, - CPV’s Central Commission for Popularization and Education |  |  |  |  |  |  |
|  |  |  | - Support to advocacy activities targeting elected bodies on the rights of all groups to be considered for the review and appraisal of laws and ordinances as well as the development and institutionalization of procedures, guidelines and tools for oversight |  |  | - UNDP, UN-HABITAT, UNICEF, UN Women |  |  | - NA (Committee of Culture, Education, Youth and Children; Committee of Social Affairs, Judicial Committee, Committee, Ethnicity Council) ONA, Training Center for Elected Representatives, Institute of Legislative Studies and selected People's Councils, - Institute for Human Rights Studies/ Ho Chi Minh National Political Administrative Academy, - CPV’s Central Commission for Popularization and Education |  |  |  |  |  |  |
| Draft Output 3.1.2: - Elected officials and bodies have improved capacities to interact and consult with citizens, especially vulnerable and disadvantaged groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Rationale: - The representative role of deputies is constrained by the formal nature of contacts with voters, insufficient resources and an incomplete legal framework. The lack of mechanisms to effectively interact with voters undermines the ability of deputies to regularly listen to voters, especially to vulnerable groups (such as women, children and ethnic minorities), and use the information provided by voters, in their deliberations, both in law-making and oversight functions as well as decision making regarding matters of national importance. An efficient and effective mechanism of interaction between the National Assembly/People’s Councils and people needs further development and institutionalization to ensure that elected bodies’ decisions reflect people’s needs and aspirations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs |  | Draft Indicators |  |  | Draft Key Actions |  | UN Agencies |  |  | Partners |  |  | Assumptions |  | Indicative Budget (US$) |
| Output 3.1.2: Elected officials and bodies have improved capacities to interact and consult with citizens, especially vulnerable and disadvantaged groups |  | Indicator 1: Number of new elected bodies’ procedures, guidelines and tools for interacting and consulting with citizens, especially vulnerable and disadvantaged groups developed. Baseline (2012): no baseline data available Target (2016): At least 10 procedures, tools and guidelines developed for interacting and consulting with citizens, especially vulnerable and disadvantaged groups. MoV: IPs quarterly and annual reports Indicator 2: Number of new ways for interacting and consulting with citizens is applied at both PPCs and NA level Baseline (2012): Successful piloting implementation of public consultations, public hearings and constituency relations in some provinces and NA committees. Target (2016): - 100% of provinces and NA committees piloting new procedures, tools and guidelines for interacting and consulting with citizens. - At least 20% of provinces institutionalizing new procedures MoV: IPs quarterly and annual reports Indicator 3: Number of consultations and interaction with all citizens, especially vulnerable and disadvantaged groups, applying developed procedures, tools and guidelines. Baseline (2012): no baseline data available Target (2016): At least 50 consultations and interaction with all citizens, especially vulnerable and disadvantaged groups, applying developed procedures, tools and guidelines. MoV: IPs quarterly and annual reports |  |  | - Advocacy targeting elected bodies to enhance interactions and consultations with citizens, especially vulnerable and disadvantaged groups. |  | UNDP, UNICEF, UNV, UN Women |  |  | - National Assembly and relevant sub-committees, Office of NA, Training Center for Elected Representatives, Institute of Legislative Studies and selected People's Councils, - Institute for Human Rights Studies/ Ho Chi Minh National Political Administrative Academy, CPV’s Central Commission for Popularization and Education, Youth Union, MOLISA |  |  |  |  | 1,480,000 |
|  |  |  |  |  | - Technical support to develop and institutionalize elected bodies’ procedures, guidelines and tools for interacting and consulting with citizens, especially vulnerable and disadvantaged groups. |  | - UNDP, UNICEF, UN Women |  |  | - NA (Committee of Culture, Education, Youth and Children; Committee of Social Affairs, Judicial Committee, Committee, Ethnicity Council), Office of NA, Training Center for Elected Representatives, Institute of Legislative Studies and selected People's Councils, - Institute for Human Rights Studies/ Ho Chi Minh National Political Administrative Academy, - CPV’s Central Commission for Popularization and Education, Youth Union, MOLISA |  |  |  |  |  |
| Draft Output 3.1.3: Enhanced knowledge management and capacity building mechanism for the National Assembly and People’s Councils. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Rationale: There is a need to advocate for institutional reform in the organization and operations of the National Assembly’s committees structure so that the functions of legislation, oversight and representation will be better performed. (The gradual shift of responsibilities from the NA Standing Committee to specialized committees; the break-out of cumbersome committees which cover too many areas); the enhancement of capacity and power of the Ethnic Council; the increase of full-time member compositions in specialized committees). Many good lessons learned and experience drawn from one NA Legislature can be transferred to the next one through good knowledge management (KM). In addition, a good KM system can provide effective supports to elected officials in their functioning. Despite their cross-cutting importance, rights-based, evidence-based, and culturally sensitive approaches are still quite new to elected officials and therefore capacity of elected officials at both national and sub-national levels should be strengthened. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Outputs |  | Draft Indicators |  | Draft Key Actions |  |  |  | UN Agencies |  |  | Partners |  |  | Assumptions | Indicative Budget (US$) |
| Output 3.1.3: Enhanced knowledge management and capacity building mechanism for the National Assembly and People’s Councils |  | Indicator 1: Proportion of elected officials having good knowledge and skills to apply a rights-based, evidence-based, and culturally sensitive approach Baseline (2012): no baseline data available by 2012 Target (2016): At least 2/3 of elected officials having good knowledge and skills to apply rights-based, evidence-based, and culturally sensitive approach MoV: IPs quarterly and annual reports (TBD/Qualitative Assessment) Indicator 2: Knowledge management mechanism (supporting facilities and resources) for elected officials set up and operational Baseline (2012): no baseline data by 2012 available Target (2016): Existence of a well-coordinated and effectively functioning knowledge management organization/unit that provide regular supports to elected officials MoV: IPs quarterly and annual reports (TBD/Qualitative Assessment) |  | - Technical support to enhance operational efficiency and effectiveness of specialized apparatus/agencies (NA’s Committees, Institute for Legislative Studies) |  |  |  | UNDP |  |  | NA (Committees, Ethnic Council, Institute for Legislative Studies, Training Center for Elected Representatives),Party Commissions, HCM National Political and Administrative Academy’s Institute of Human Rights, Local People’s Councils |  |  |  | 200,000 |
|  |  |  |  | - Technical assistance to set up and maintain a knowledge management mechanism (enhanced and sustainable supporting facilities and resources) for elected officials |  |  |  | - UNDP |  |  | - NA |  |  |  |  |
|  |  |  |  | - Capacity building for elected officials on rights-based, evidence-based, and culturally sensitive approach |  |  |  | - UNDP, UNESCO, UN Women |  |  | - NA, CEMA, MOCST, NA Ethnicity Council, ONA |  |  |  |  |

| Draft Outcome 3.2: By 2016, all citizens, particularly the most vulnerable and disadvantaged groups, benefit from strengthened legal and judicial reform and increased access to justice, enhanced capacity of legal and judicial professionals, and strengthened national legal frameworks to support the implementation of international conventions ratified by Viet Nam |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Draft Output 3.2.1: Policy, legal and regulatory framework strengthened to better reflect the rights of the most vulnerable groups, and increase their access to justice |  |  |  |  |  |  |  |
| Rationale: In the national report submitted to the Human Rights Council by the Government of Viet Nam, inconsistencies, conflicts and overlaps in the legal system were described as the “main obstacle to the development of the society and the exercise of human rights. The National report also highlights the incomplete awareness on the part of some public servants at national and local level in terms of human rights law, Viet Nam’s treaty obligations and even national laws and policies. Greater international integration (including further accession to international human rights instruments) will heighten the need for effective systems for implementation and monitoring of Viet Nam’s compliance with its international treaty obligations. With the mandate of supporting Viet Nam in achieving its international obligations and comparative advantages in policy advice, the UN will support the on-going implementation of the legal reform and judicial reform, including advocacy and technical assistance for transposition into domestic legal legislations and policies of international treaties to which Viet Nam is a party, development/amendment and implementation of key legislation related to protection of rights and access to justice, and monitoring and evaluation of Strategy for the development and implementation of Viet Nam’s legal system, judicial reform strategy and other relevant national strategies and programmes. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners |  | Assumptions | Indicative Budget (US$) |
| Output 3.2.1: Policy, legal and regulatory framework strengthened to better reflect the rights of the most vulnerable groups, and increase their access to justice | Indicator 1: Number of policy recommendations developed by the UN to better reflect the rights of the most vulnerable and disadvantaged groups Baseline (2011): not available Target (2016): TBD with Government MoV: TBD with Government | - Provide technical assistance for ratification, reporting and follow-up actions of international treaties, and transposition into domestic legal legislations and policies of international treaties to which Viet Nam is a party | ILO, UNDP, UNICEF, UNODC, UN Women | MOFA, MOJ, MOLISA, MPS, Office of the Government, National Steering Committee on Human Rights, National Assembly, Supreme People’s Procuracy (SPP), Supreme People’s Court (SPC), Communist Party (Central Judicial Reform Steering Committee), PSPMOs (including VGCL, VCCI, VCA, Viet Nam Bar Federation (VBF), Viet Nam Law Association (VLA), Viet Nam Women’s Union (WU), Viet Nam Association for Protection of Children’s Rights (VAPCR) |  |  | 14,130,000 |
|  |  | - Support the development/amendment and implementation of key legislation related to protection of rights and access to justice, particularly in respect of legal empowerment of the most vulnerable and disadvantaged groups, including the poor, women, children, ethnic minorities, victims of violence, exploitation and abuse, victims of human trafficking, victims of environmental pollution, migrant, people living with HIV/AIDS, people with disabilities etc. | - IOM, UNAIDS, UNDP, UNICEF, - UNODC - UN Women | - NA (Social Affairs Committee, Ethnicity Council), MOJ, MOLISA, MPS, SPP, SPC, WU, VAPCR |  |  |  |
|  |  | - Support strategic planning, implementation and M&E of national legal reform, including capacities for research, data collection and analysis in support of evidence-based policy making. | - UNDP, UNICEF, UNODC | - NA, PCC, MPI, Ministry of Finance, MOLISA, MPS, MOJ |  |  |  |
|  |  | - Support the development of monitoring frameworks and mechanisms for implementation of National Strategies and Programmes related to protection of rights and access to justice, including the National Targeted Program on Crime Prevention, National Targeted Program on Control of Narcotic Drugs, National Programme against Human Trafficking, National Programme against Prostitution and relevant national programs and projects | - IOM, UNDP, UNICEF, UNODC | - MPS, MOLISA, MOJ |  |  |  |
| Draft Output 3.2.2: Law enforcement and judicial institutions strengthened to better protect rights, and provide increased access to justice to all people, particularly the most vulnerable groups |  |  |  |  |  |  |  |
| Rationale: Viet Nam’s Judicial Reform Strategy to 2020 sets out a challenging agenda. Further institutional reforms are needed within courts, procuracies and other agencies, as well as to criminal, civil and administrative procedures, in order to bring them fully in line with applicable international human rights standards as well as implementing Strategy’s directions. The response of the formal justice system, including the police and courts, needs to be more sensitive to the needs of women and children experiencing violence, in particular by supporting them more effectively to end abuse and violence. The UN, with the mandate of supporting Viet Nam in achieving its international obligations and comparative advantages in policy advice, will support Viet Nam in the implementation of the judicial reform, focusing on institutional reforms of the law enforcement structures and court system. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners |  | Assumptions | Indicative Budget (US$) |
| Output 3.2.2: Law enforcement and judicial institutions strengthened to better protect rights, and provide increased access to justice to all people, particularly the most vulnerable groups | Indicator 1: Number of institutional reforms implemented to better protect the rights of the most vulnerable and disadvantaged groups Baseline (2011): Data identified in the current Govt.’s judicial reform strategy and plan Target (2016): Increased number of institutional reforms implemented MoV: Report of the Central Judicial Reform Steering Committee Indicator 2: Extent to which the rights of children in contact with the justice system are reflected in key legislation Baseline (2011): Penal Procedure Code currently stipulates some special procedures for children in conflict with the law only. Target (2016): child friendly procedures, for all children in contact with the law reflected in the Penal Procedure Code. MoV: MoJ report and Penal Procedure Code | - Support strategic planning, implementation and M&E of national judicial reform programmes, including capacities for research, data collection and analysis in support of evidence-based policy making | UNDP, UNICEF, UNODC | MOJ, MPS, CPV (Central Judicial Reform Steering Committee), SPC, SPP, PSPMO (including VLA, VBF, and others) |  |  | 11,450,000 |
|  |  | - Support the introduction and implementation of appropriate enhancements of professional standards, oversight, coordination and cooperation mechanisms in law enforcement agencies, prosecution office and judiciary. | - ILO, UNDP, UNODC | MOLISA, MPS, MOJ |  |  |  |
|  |  | - Support the development and implementation of investigation, prosecution and adjudication procedures which are child friendly and gender sensitive and in compliance with Viet Nam’s international commitments. | - UNDP, UNICEF, - UNODC, - UN Women | MOJ, MPS, SPP, SPC, MOLISA, Viet Nam Lawyers Association (VLA), Viet Nam Women’s Union (WU), Viet Nam Association for Protection of Children’s Rights (VAPCR) |  |  |  |
|  |  | - Advocate and provide technical assistance for reform of the Court system, including advocate for and support the establishment of specialized court for families and juveniles | - ILO, UNDP, UNICEF, UNODC | - NA, Party Central Committee (PCC), MOJ, MOLISA, MPS, SPP, SPC |  |  |  |
|  |  | - Provide technical assistance and advocate for strengthening law enforcement structures for dealing with specific crime types, including establishment of specialized child protection police units | - UNDP, UNICEF | - MPS, SPP, SPC, MOJ, MOLISA, VLA |  |  |  |
| Draft Output 3.2.3: Awareness raising programmes and legal support services developed and effectively implemented to enable all people, particularly the vulnerable groups to be aware of, and claim their rights |  |  |  |  |  |  |  |
| Rationale: People’s awareness of their rights and how to enforce them is still low. Full accountability under law also requires strengthening access to justice, particularly for the vulnerable and disadvantaged people who depend on the law to protect them. With recognized comparative advantage of advocating for the most disadvantaged and vulnerable people, the UN will support to address these constraints through providing technical assistance for the development and implementation of awareness raising programmes, legal assistance and other relevant support services to empower claim holders, particularly the most vulnerable and disadvantaged groups to be aware of their rights and help them enforce those rights. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners |  | Assumptions | Indicative Budget (US$) |
| Output 3.2.3: Awareness raising programmes and legal support services developed and effectively implemented to enable all people, particularly the vulnerable groups to be aware of, and claim their rights | Indicator 1: Number of people receiving free legal assistance to protect/enforce their rights Baseline (2011): not available Target (2016): increased number of people receiving free legal assistance MoV: reports from national legal aid agencies and other service providers, PSPMOs Indicator 2: Number of children in conflict with the law who benefited from diversion programmes Baseline (2011): not available Target (2016): increased number of children who benefited from diversion programmes MoV: reports from MPS, SPP, SPC | - Support development of free legal advisory services to raise legal awareness and provide legal assistance to the most vulnerable and disadvantaged groups, including the poor, women, children, ethnic minorities, victims of violence, exploitation and abuse, victims of human trafficking, victims of environmental pollution, migrant workers, people living with HIV, people with disabilities etc. | ILO, IOM, UNAIDS, UNDP, UNICEF | MOH, MOJ, MPS, MOLISA) SPC, SPP PSPMOs, VAPCR, (including VGCL, VCCI, VCA, VLA, VBF, VWU and others), law universities, People’s Committees |  |  | 7,700,000 |
|  |  | - Support awareness raising activities on protection of rights and access to justice, especially for the most vulnerable and disadvantaged groups | - ILO, IOM, UNAIDS, UNDP, UNICEF, UNODC, UNV, UN Women | MOH, MOJ, MPS, MOLISA, SPC, SPP PSPMOs, (including VLA, VBF, VWU, VGCL, VCCI, VCA VAPCR and others), law universities, - People’s Committees, - PPCs |  |  |  |
|  |  | - Support the development and implementation of child friendly and gender sensitive services in judicial, administrative and community-based processes | - UNDP, UNICEF, UNODC, - UN Women | MOJ, MOLISA, MPS, SPP, SPC, WU, VAPCR, VLA |  |  |  |
| Draft Output 3.2.4: Legal, law enforcement and judicial personnel have enhanced knowledge and skills to carry out their obligations under Vietnam’s Constitution and laws as well as ratified international conventions |  |  |  |  |  |  |  |
| Rationale: The system of legal education is in urgent need of reform. Public servants who draft and enforce the laws do not yet have adequate knowledge and understanding of the principles of the rule of law and Viet Nam’s international commitments on protection of rights. With recognized comparative advantage in supporting capacity building efforts for individuals, organizations/agencies and system over the long term, the UN will support the enhancement of capacity for duty bearers, including legal, law enforcement and judicial personnel, to carry out obligations under Viet Nam’s Constitution and laws as well as international conventions to which Viet Nam is a party. |  |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions |  | Indicative Budget (US$) |
| Output 3.2.4: Legal, law enforcement and judicial personnel have enhanced knowledge and skills to carry out their obligations under Vietnam’s Constitution and laws as well as ratified international conventions | Indicator 1: Number of legal, law enforcement and judicial personnel trained to effectively implement their obligations under Vietnam’s Constitution and laws as well as international conventions to which Viet Nam is a party Baseline (2011): not available Target (2016): increased number of people trained MoV: reports from MPS, SPP, SPC Indicator 2: Percentage of people satisfied with the performance of legal and judicial personnel Baseline (2011): UNDP 2010 Access to Justice survey Target (2016): Increased percentage of people satisfied with the performance of legal and judicial personnel MoV: UNDP 2016 Access to Justice survey | - Provide technical assistance to strengthen capacity of legal, law enforcement and justice agencies, and labour inspectorates for improved crime prevention & response, protection of rights and justice for vulnerable groups, especially women and children | UNDP, UNICEF, UNODC | MOJ, MPS, MOLISA, MOFA, National Human Rights Committee, NA, SPC, SPP, law universities, PSPMO (including VLA, VBF, VWU and others), People’s Committees |  |  | 9,100,000 |
|  |  | - Support capacity building activities to strengthen implementation of Viet Nam’s international commitments | - ILO, UNDP, UNESCO, - UNICEF, UNODC, - UN Women | - MOCST, MOFA, PPCs, MPS, SPP, SPC, MOJ, MOLISA, VGCL, VCCI |  |  |  |
|  |  | - Provide technical assistance to strengthen university legal education programmes | - UNDP | - law universities |  |  |  |

| Draft Outcome 3.3: By 2016, improved performance of the public sector institutions at national and sub-national levels, through enhanced coordination, accountability, transparency and anti-corruption efforts, will reduce disparities and ensure access to public services for the most vulnerable and disadvantaged groups |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 3.3.1: Government agencies at the sub-national level are able to apply an evidence-based and cross-sectoral approach to planning and sectoral policy formulation and application to deliver basic public services for the most vulnerable and the disadvantaged groups |  |  |  |  |  |  |
| Rationale: The review of 10 year (2001-2010) SEDS and 5 year SEDP (2006-2010) has highlighted the need to strengthen coordination among the government agencies for effective functioning of the Viet Nam administrative system. The next 10 year SEDS (2011-2020) has further emphasized the need to make vigorous progress in administrative reform by ensuring efficient coordination among the various government agencies. Government and UN analytical work has highlighted the need to improve the horizontal and vertical coordination coupled with comprehensive capacity building for effective functioning of public service institutions especially at the decentralized level. The key strategies that will be used to achieve the outputs are advocacy; capacity development and demonstration of pilot/innovative approaches. The UN will support demonstration of integrated basic services and will undertake comprehensive capacity development to build capacity of local authorities in planning and management of integrated and cross-sectoral programming. Advocacy will be undertaken in key areas such as the establishment of formal cross-sectoral coordination mechanisms that will contribute to improved basic public service provision to vulnerable groups, cross-sectoral policy monitoring and mainstreaming children’s participation in local development processes. UN has significant comparative advantages to work in selected provinces to improve local capacity to manage public investment programmes and projects effectively. In the current cycle, demonstration of multi-sectoral and integrated approaches to tackle children’s issues at local level has contributed to improving the cross-sectoral coordination of public services by various government agencies and the UN aims to build upon these initiatives and achieve the above-mentioned output. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 3.3.1: Government agencies at the sub-national level are able to apply an evidence-based and cross-sectoral approach to planning and sectoral policy formulation and application to deliver basic public services for the most vulnerable and the disadvantaged groups | Indicator 1: - Availability of system and tools in selected provinces for cross-sectoral planning, implementation and monitoring of basic public services Baseline (2011): In 3 provinces, some informal mechanisms are in place such as the cross-sectoral group for provincial planning Target (2016): In selected provinces formal mechanism (provincial guidelines, coordination mechanism) established and functioning MoV: Provincial official documents that institutionalize the coordination mechanism; Provincial reports on progress of cross-sectoral planning, implementation and monitoring of basic public services. - Indicator 2: - Number of cross-sectoral plans developed and being implemented in selected provinces. Baseline (2011): currently no such plans exist in the provinces Target (2016): at least 2 cross-sectoral plans in each province are developed and being implemented. MoV: Progress reports against the implementation of the plan | - Support development of integrated and multi-sectoral convergent basic public services and policies in selected provinces. | ITC, UN-HABITAT, UNICEF | Quang Nam PPC and other selected provinces, People’s Committees of selected provinces, MPI, MOLISA |  | 6,200,000 |
|  |  | - Support comprehensive capacity development and system strengthening to enhance the performance of government institutions to undertake, evidence-based and cross-sectoral programming approaches with a focus on addressing key social issues for the most vulnerable and the disadvantaged groups. | - IOM, ITC, UNDP, UNESCO, UN-HABITAT, UNICEF | HCMC Institute of Development Studies (IDS), Academy of Managers of Construction and Cities (AMC) |  |  |
|  |  | - Support strategic initiatives and approaches to enhance community participation (including that of children and women) in local planning, budgeting and service delivery process. | - UNICEF, - UNV | MPI, MOLISA People’s Committees of selected provinces |  |  |
| Draft Output 3.3.2: The public administration systems at national level and in selected provinces, have enhanced human resource management systems, a customer-oriented approach, and strengthened mechanisms for accountability and transparency |  |  |  |  |  |  |
| Rationale: The official review of ten years of implementation of the PAR Master Plan together with other sources, including UN analysis, suggest that the need to improve performance of the public sector and accountability and transparency in the public administration performance at the central and local levels has been highlighted in different policy discussions. At the local level it becomes imperative, as Viet Nam moves towards a higher level of human development, to enhance the interactions and relationship of three mutually reinforcing processes: policymaking, policy implementation and public service delivery (including monitoring and evaluation systems). |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 3.3.2: The public administration systems at national level and in selected provinces, have enhanced human resource management systems, a customer-oriented approach, and strengthened mechanisms for accountability and transparency | Indicator 1: - Number of provinces that monitor service provision and performance through the use of social audits tools Baseline (2011): 4 provinces pilot social audit tools Target (2016): Institutionalization of use of social audit tools in these provinces MoV: Reports from provincial authorities Indicator 2: Number of public administrative agencies with transparent and accountable human resource development procedures as per new Law on Public Officials and Civil Servants (LPOCS) Baseline (2011): Early stages of implementation of the LPOCS Target (2016): Central level administrative agencies implementing transparent and accountable human resources development procedures MoV: Annual government reports on law implementation. | - Strengthen capacities for social accountability tools in selected provinces to monitor public service provision and performance | UNICEF | MPI, PPC, DPI, line departments of selected provinces |  | 4,160,000 |
|  |  | - Support capacities of accountability institutions, including the media, to monitor implementation of public policies | - UNDP, - UNESCO | - MOIC, Viet Nam Journalist Association |  |  |
|  |  | - Support strengthening of human resource capacities in the public sector, including appointment, selection, recruitment, performance assessment and incentives. | - UNDP | - MoHA, MoLISA, CCOP, - Da Nang, |  |  |
|  |  | - Support institutional reforms, including governmental organizational reform | - ILO, UNDP | - MoLISA, MoHA |  |  |
| Draft Output 3.3.3: Selected National Institutions have enhanced capacities to implement and monitor implementation of national legislation on anti-corruption and key provisions of the UN Convention Against Corruption (UNCAC) |  |  |  |  |  |  |
| Rationale: Corruption is a systemic development problem in Viet Nam as has been recognized at the highest levels of the policy-making process in the country. Resolution No. 21/2009/NQ-CP dated 12 May 2009 on the National Strategy for Preventing and Combating Corruption Towards 2020 highlights that “corruption is still happening seriously and complicatedly. It causes great damage in many aspects, erodes the people’s confidence in the Party leadership and state management and threatens existence of the socio-economic regime.” The main causes for the existence of corruption in the country are diverse and manifold, but as recognized by Resolution No. 21/2009/NQ-CP, they include a great deal of weaknesses in the public administration system. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 3.3.3: Selected National Institutions have enhanced capacities to implement and monitor implementation of national legislation on anti-corruption and key provisions of the UN Convention Against Corruption (UNCAC) | Indicator 1: Number of cases investigated and prosecuted Baseline (2011): Number of cases as reported in the 2010 Ministry of Public Security report Target (2016): Increase in the number of prosecuted cases brought to the Court MoV: Annual report by the Ministry of Public Security Indicator 2: Frequency of review of implementation of national legislation on anti-corruption and key provisions within the UN Convention Against Corruption (UNCAC) Baseline (2011): Ongoing processes of reviewing compliance with UNCAC and review of 5 years of implementation of anti-corruption law. Target (2012): Periodic assessment of implementation of UNCAC and anti-corruption law through an institutionalized monitoring and evaluation mechanism MoV: Reports of the Government to the Conference of State Parties of UNCAC | - Support identification and investigation of corrupt practices, bribery and money laundering activities by state agencies | UNDP, UNODC | Economic Police Department (MOPS), Anti-corruption Department (MOPS), Counter narcotic Department (MOPS), Ministry of Justice, Border Army, Customs General Department (MOF), Supreme People's Court, Government Inspectorate, of Vietnam/ AMLD, media organisations |  | 6,550,000 |
|  |  | - Provide substantive, policy and technical advice and assistance in the field of anti corruption, to develop and implement legislation, policies, and procedures, as well as raise awareness among public and private sector institutions of their responsibilities in relation to corruption prevention, handling and monitoring | UNDP, UNODC |  |  |  |
|  |  | - Capacity building for national institutions to implement and monitor implementation of national policies on anti-corruption and UN Convention against Corruption | UNDP, UNODC |  |  |  |
|  |  | - Capacity building for media in ethical and professional communication standards to ensure accountable reporting on anti-corruption, bribery and money laundering | UNESCO, UNODC |  |  |  |
| Draft Output 3.3.4: Systems to monitor the performance of government institutions and the delivery of basic public services are evidence-based and include mechanisms for citizen feedback |  |  |  |  |  |  |
| Rationale: Overall, it has been well recognized that monitoring and evaluation of public investment programmes and projects receives low attention which has made it difficult for the public to judge whether the selection of these programmes and projects has been right or wrong and whether the use of public resources has been efficient or not. Access to information is still rather limited, including objective and evidence-based assessment of the quality of public services delivered by administrative agencies. While ensuring use of data and information for planning and evaluation of public investment programmes and projects, there is a need to strengthen feedback and transmission mechanisms from citizens on the quality of public services and their impact on their own development needs in order to ensure effective implementation of government decisions and improvement of service delivery. The current efforts and approaches to administrative reform contribute to tackling issues formalistically and are mostly focused at the input level, but are not leading to deep changes required in middle-income countries nor to better monitoring of outputs and outcomes in the provision of public administration functions. The key strategies to achieve the above output are knowledge generation and management, advocacy and capacity development. The UN has extensive experience of working on the ground in the area of Public Administration Reform, evidence based policy advocacy, and a human right based approach. With its recent initiatives to develop the Public Administration Performance Index (PAPI), Social Audit for SEDP M&E and Provincial Situation Analysis of Children, the UN aims to build upon these initiatives to achieve the above output and contribute to strengthen the M&E system for improved assessment of the performance of government institutions. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 3.3.4: Systems to monitor the performance of government institutions and the delivery of basic public services are evidence-based and include mechanisms for citizen feedback | Indicator 1: Availability of data and information in selected provinces for evidence-based assessment of government institutions and delivery of public services for the most vulnerable Baseline (2011): Availability and quality of data -disaggregated by sex, age and ethnicity- limited Target (2016): 3 Provincial Situation Analyses of children under taken and 3 existing ones updated MoV: annual reports Indicator 2: Number of M&E systems and feedback mechanisms implemented, evaluated and replicated Baseline (2011): PAPI in 2010 in 30 provinces Target (2016): Annual PAPI in all 63 provinces MoV: annual PAPI reports | - Conduct research/study, situation analysis to provide data and information - that highlights disparity and inequity - to increase access to basic public services among the most vulnerable and establish baseline for impact assessment | UNICEF | MPI, MoLISA, Provincial People’s Committees |  | 9,700,000 |
|  |  | - Support development of objective-based monitoring systems on governance and public administration performance at provincial and national levels | - UNDP | Vietnam Fatherland Front (VFF), Government Inspectorate, Ministry of Home Affairs /Ministry of Public Security, National Assembly, PSPMOs |  |  |
|  |  | - Provide evidence-based policy advices and facilitate policy dialogues to strengthen its implementation in selected provinces. | - UNDP, UNICEF | - MPI, MoLISA, MoHA, VFF, - Provincial People’s Committees |  |  |

| Draft Outcome 3.4: By 2016, political, social, professional and mass organisations (PSPMOs) participate effectively in policy discussion and decision-making processes for the benefit of the most vulnerable and disadvantaged groups |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Draft Output 3.4.1: Enabling legal, policy and institutional framework available for PSPMOs to participate in policy discussion and decision-making processes |  |  |  |  |  |  |
| Rationale: According to Viet Nam’s and UN’s reports, the issues are: “The Party’s policies on national unity has not been fully institutionalized or implemented. Hence the participation of the people organizations and people to the movement and campaign of the Fatherland Front has been limited” (The Party’s Political Report at the 11st Party’s Congress 2011) “Improve mechnisms for the people to contribute opinions, social feedback and to oversee the work of the Party and the State, especially on socio-economic policies and important plans, master plans, projects and programs. Provide regulations on providing information and the state accountability of State agencies to the people.” (Socio-Economic Development Strategy 2011 – 2020) “Strengthen capacity and create mechanisms for the people to implement fully the rights of the Master, particularlly direct democracy, to promote strongly all creative abilities and to endure a high consensus in the society to create the motive for the country’s development” (Socio-Economic Development Strategy 2011-2020) ” insufficient and unclear legal frameworks as a main factor to enhance the impact of these organizations in holding the state accountable, influencing public policies and ensuring responsiveness of government to people’s concerns” (UN analytical work) To address these issues, UN will provide technical assistance, advocate and support for the participation of PSPMOs to participate in policy discussion and decision-making processes. The UN will bring global experiences and good practices from other countries. This is a UN comparative advantage as the UN has had models of good practices and a broad range of experience of PSPMOs’ participation in the process of decision and policy making, and net-working. UN can also increase the space for PSPMOs to participate in policy dialogue with the Government. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 3.4.1: Enabling legal, policy and institutional framework available for PSPMOs to participate in policy discussion and decision-making processes | Indicator 1: Number of policies, legal documents and guidelines developed facilitating the participation of PSPMOs Baseline (2011): The Party’s documents and legal documents on the participation of PSPMOs Target (2016): Additional Party documents and legal documents facilitating the participation of PSPMOs MoV: newly promulgated documents Indicator 2: Percentage of legal and policy discussions hosted jointly by the Government and the UN includes PSPMOs Baseline (2011): no data Target (2016): > 50% of legal and policy discussions hosted jointly by the Government and the UN include PSPMOs MoV: UN-Government reports | - Provide technical assistance and advocate for the improvement of laws, policies, norms and guidelines, including the sharing of good international practices to strengthen PSPMOs participation | ILO, UNAIDS, UNDP, UNICEF, UN Women | PSPMOs, Party’s Central Commissions, MoHA, line ministries, National Assembly |  | 5,500,000 |
|  |  | - Support and/or facilitate consultative process for the improvement of participation of PSPMOs | ILO, UNDP, UNICEF, UNV, UN Women | PSPMOs, Party’s Central Commissions, MoHA, line ministries, National Assembly |  |  |
|  |  | - Provide technical assistance to implement, evaluate, document and replicate innovative interventions and models | ILO, UNDP, UNICEF, UN Women | PSPMOs, MoHA, line ministries |  |  |
| Draft Output 3.4.2: PSPMOs’ human resources and organisation capacities strengthened to provide significant contributions in the development of policies in the best interests of the most vulnerable groups |  |  |  |  |  |  |
| Rationale: According to Viet Nam’s and UN’s reports, the issues are: “Strengthen capacity and create mechanisms for the people to implement fully the rights of the Master, particularlly direct democracy, to promote strongly all creative abilities and to endure a high consensus in the society to create the motive for the country’s development” (Socio-economic Development Strategy 2011-2020) “the structure of some social and political organizations has not been streamlined, effective with unclear functions, responsibilities and relations” (The Party’s Political Report at the 11st Party’s Congress 2011) “inadequate (independent) funding, capacities and networking” (UN analytical work) - This output is intended to focus on inward reviewing of current gaps and existing challenges in the PSPMO’s coordination system as well as identified as ”insufficient and unclear legal frameworks” and “overlapping roles among government and mass organizations “ (UN analytical work) To address these issues, the UN will support strengthening the capacity and the coordination of PSPMOs. - The UN convening power will play an importance role in supporting the coordination of PSPMOs. |  |  |  |  |  |  |
| Draft Outputs | Draft Indicators | Draft Key Actions | UN Agencies | Partners | Assumptions | Indicative Budget (US$) |
| Output 3.4.2: PSPMOs’ human resources and organisation capacities strengthened to provide significant contributions in the development of policies in the best interests of the most vulnerable groups | Indicator 1: Number of PSPMOs who constantly provide significant contributions for the development of legal and policy discussions for the benefit of the most vulnerable groups of population Baseline (2011): not available Target (2016): Increasing number of PSPMOs who constantly provide significant contributions for the development of legal and policy discussions MoV: Documents from PSPMOs Indicator 2: Number of joint activities among PSPMOs and/or with private sector supported by the UN Baseline (2011): not available Target (2016): Increasing number of joint activities among PSPMOs and/or with private sector supported by the UN MoV: UN reports | 1.Support advocacy, leadership and management skills/capacities of PSPMOs | ILO, UNDP, UNICEF, UNESCO, UN Women | PSPMOs, MoHA, line ministries. |  | 5,270,000 |
|  |  | 2. Provide technical assistance to improve coordination and networking among PSPMOs and with the private sector | ILO, UNAIDS, UNDP, UNICEF, UN Women | - PSPMOs, MoHA, line ministries, private sector |  |  |

Operationalised is defined as: “the process in which the UN together with relevant duty bearers and right holders, has identified policy issues, develop an appropriate policy response and provides assistance in executing the policies through for example guideline development, training of staff and the establishment of monitoring and evaluation systems”.

including the disadvantaged women, children, elderly, disabled, migrants, ethnic minorities

including the energy supply which should ensure access to renewable energy sources for the poor

The strategy will take into account sustainable human development, and appropriate monitoring, reporting and verification systems are established and operationalized in accordance with the UN Framework Convention on Climate Change and the UN Convention to Combat Desertification (UNCCD)

The selected pillars under this Outcome bear a close linkage with UN support to broader policy reduction efforts (addressing systemic factors and the enabling environment) and labour market policies, which are grouped under UN Focus Area 1.

Given its specificity, expansion of health insurance is dealt with under Outcome 2.2 (Health).