### Country:		MÉXICO

### COUNTRY PROGRAMME PERFORMANCE SUMMARY

### Reporting period: 	2008-2013

### I.  EXECUTIVE SUMMARY (1/2 page maximum)

According to the latest HDI, Mexico ranks 57 out of 187 countries, maintaining the same position over the last 3 years. The country’s GDP growth (4% in 2011) surpassed that of many LAC and OECD partners, with 3.8% inflation. Although Mexico is still recovering from the GDP falls in 2009 and is facing increased criminal violence, the country remained stable and both economic and social indicators showed improvement, notably on job creation (Mexico created additional formal 800,000 jobs in 2010 and 600,000 in 2011). Unemployment is at 4.5%, one of the lowest of LA. According to the latest National MDG report, Mexico has achieved, or is on its way to achieving, most MDGs with the exception of maternal mortality and women´s political participation.

Poverty has remained at the same level while severe poverty minimally decreased mostly due to Mexico's counter-cyclical economic and social policies. However, only 19% of the Mexican population is free of all faces of the multi-dimensional poverty. The rest of the population lack access to quality education, housing, basic services, social security, health services or access to basic food. In 2011, social programmes such as Oportunidades reached coverage of 5.8 million families supporting a quarter of the national population with a budget of almost 58 billion pesos, about half a percentage point of GDP. Mexico also achieved universal health coverage mostly due to a successful implementation of Seguro Popular, a free health coverage scheme for the uninsured poor.

Inequities among states, gender and ethnic groups persist in Mexico. The HDI in the most developed state (Distrito Federal) is 24% higher than in the poorest state (Chiapas).  Among the Indigenous people, 3 out of 4 are multi-dimensionally poor. Municipalities that are predominantly indigenous tend to achieve lower levels of HD and have higher gender inequalities: in such municipalities 50.6% of women do not complete primary school, compared to 42.1% for men.

In 2007, the Government of Mexico (GoM) and UNDP Mexico signed a Country Programme Document (CPD) for 2008-2012, which is fully aligned with the National Development Plan.  The programme, developed through a process of dialogue and consensus building, aims to help reduce poverty and economic, social, gender and ethnic inequality, strengthen democratic governance, and increase systemic competitiveness and environmental sustainability.  The programme strategies are based on the Common Country Assessment (CCA) and fully aligned with the UNDAF 2008-2012 as well as UNDP’s Global Strategic Plan 2008-2011.

Since Mexico’s graduation as a Net Contributor Country (NCC) in 2008, UNDP has maintained its presence in Mexico as a trusted partner to address the country´s development challenges. In 2011, Mexico passed International Development Cooperation Law (LCID) and established Mexican Agency for International Development Cooperation (AMEXCID) adopting an innovative approach with a dual nature as an aid provider and recipient. To strengthen its capacities to foster its international cooperation, Mexico and UNDP signed a Strategic Partnership Agreement establishing a South-South and Triangular cooperation dynamics in the region in September 2011.

The CPD identifies 6 thematic priorities under which the CO supports the adoption of public policies, provides technical assistance to support national actions, and promotes public awareness of sustainable human development and MDGs. These thematic priorities have been promoted through strengths national capacities, systematize and disseminate best practices, and transfers useful international experiences.

The 2012 July elections hold keys to shape the political agenda for the following years in Mexico. Seven state governments, fifteen local congresses, and nearly a thousand municipal governments were elected together with President and Congress.  In addition to the importance in terms of Mexico's democratic transition and the new government's policy orientations, the elections ranked high on the CO's agenda due to UNDP's direct responsibilities in the electoral observation process and the protection of federal social programmes against misuse of these resources during the run-up to the elections in Mexico.  During the political transition from July through December 2012, the CO faced opportunities and potential challenges in its positioning and continuous inclusion of UN values such as human rights based approach, protection and inclusion of vulnerable groups into the national development agenda of the new administration.

In order to align the actions of the United Nations System in Mexico with the National Development Plan for the now current federal administration, and thereby improve coordination among all national and international actors to address development challenges in Mexico, UNDAF/CPD were extended for 1 year until 31 December 2013. New process to formulate the next cycle of UNDAF started in December 2012.

### II: Country Programme Performance Summary

| Country information |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country name: Mexico |  |  |  |  |
| Current country programme period: 2008-2013 |  |  |  |  |
| Outcomes |  | Total Expenditure | Key Indicators of outcome (1-4 per outcome) | Progress made against key indicators |
| Public policies have had a positive impact on the achievement of MDG´s, fostering human development and social responsibility. |  | $ 6,992,658 | - Government includes Human Development concept as a tool to identify possible policy options. - Chiapas government incorporates Human Development Report as a tool to implement public policy facing population dispersion. | - Final document of fourth Mexican HDR on public expenditure and Chiapas HDR were released in 2011, launch of document of women and the public expenditure on January 17th 2011 at UN House México. HDI Database with information from the National Household Survey from 2000-2008, completed. Advances in Technical support provided to Federal Program Oportunidades (Conditional Cash Transfers Program). Also the HDR of Estado de México was launched. - Public policies oriented to human development promotion and poverty reduction in the State of Chiapas. |
| UNDP Contribution: The three national human development reports that UNDP Mexico has delivered to date all have a common focus on inequality. In 2011, UNDP produced 3 landmark HDR: one of public expenditure, showing that there is fiscal space to provide direct benefits to the most vulnerable groups; another of indigenous peoples, showing that they are still one of the most backward segment of Mexican society with high levels of poverty and low levels of human development; and a final one on the State of Mexico, showing that the second most dynamic local economy is not achieving the same pace in terms of HD success. UNDP also publishes every 2 years the "Social Competitiveness Index," a multi-faceted index that collects and processes data on the length of the workday, child labor, access to health care, poverty, wages and the formal labor market, providing key data on the welfare of the population. |  |  |  |  |
| Social competitiveness policies are implemented for the progress of the economy and productive chains. | $10,776,469 |  | - External evaluation of FIRA - UNDP Microfinance project. - Assistance provided to FIRA on methodologies to integrate microcredit recipients into rural value chains. - Number of enterprises that received technical assistance with the Methodology for Supplier Development and number of enterprises that have registered in the portals. - Supply Development Programme methodology transferred to Latin America UNDP CO's - SME's have been certified and trained in business management techniques and processes as required by the aerospace sector. | - Microfinance institutions were diagnosed and improvement programmes outlined. - FIRA, the largest funder of rural development has now a much stronger microfinance unit. The issues of industrial policy are much more widely accepted by federal and state authorities. - Over 200 companies, large and small will have benefited their sales and increased employment from the application of the SDP (Supplier Development Programme). Increasingly the SMES assisted are suppliers of large public companies in the energy sector. - At least 2 value chains in Honduras receive the SDP. - 28 aerospace industry certification process, NADCAP or AS9100 were implemented in Mexico's large, small and medium enterprises. |
| UNDP Contribution: UNDP has worked with the Federal Government, the Congress, the State governments and private sector to improve the competitiveness of the productive sector through the formulation of development plans and policies. Analysis of value chains and evaluation of cross-sectorial policy application have contributed to improve competitiveness across various value chains. Supplier Development Program has integrated small and medium enterprises (SMEs) into large Mexican trade and financial flows, resulting in strengthening the national economy through: 1) creation of new employment, 2) increasing indirect exports by raising the value-added of local content, and 3) the creation of competitive local supply chains. UNDP also provided technical assistance to FIRA, the largest financial institution for rural development to support SMEs in order to promote their productive integration in the economy. |  |  |  |  |

| Management processes, policies and citizenship are strengthen for sustainable development | $32,953,804 | - Number of participation venue created and operating at national, regional and state levels. - Number of training and workshops for civil participation - Counsels actively participate in CCDS - Number of CSOs that represent women, youth, and indigenous community participate actively in the activities and projects related to environmental policy. - Key meetings with stakeholders at the local carried out - Capacity development programme designed and key partners for implementation identified | - During 2010 the Project focused on strengthening civil society participation in 3 sectors: indigenous people, young people and gender oriented groups. The 3 groups developed statements regarding their position on climate change which were posted in the Minister of Environment’s webpage. - Meetings of Councils were held regularly and involving more counselors than in previous years, communication was also strengthened. The councils, through the project are producing their own products such as Statistics Environment Database, and publications such as the “Environment in numbers”. - The project carried out a number of meeting as well as project induction workshop with stakeholders that include local authorities, producers association, indigenous communities, and civil societies. - Capacity Development Programme was designed and waiting to be implemented. - Baseline was established during the process to define the PRODOC. The baseline was updated during the induction workshop in consultation with stakeholders. |
| --- | --- | --- | --- |
| UNDP Contribution: The portfolio of Environment and Sustainable Development has supported conservation and sustainable use of biodiversity, strengthening citizens’ participation in sustainable development, and integration of the concept of sustainable resource management in poverty reduction strategies and development plans. It has strengthened local capacities to adopt effective environmental governance, innovation and financial mechanisms for the distribution of environmentally sustainable technologies. In the last few years, UNDP Mexico has focused on supporting the GoM to develop sustainable development pathways that will lead to low-emission development and resilience to climate change. As a result of the intensive collaboration between the Congress and UNDP on Climate Change, the Senate unanimously passed a comprehensive bill on Climate Change. UNDP additionally provided support to the National Adaptation Strategy which outlines a way forward with respect to the institutional capacity development and concrete sectorial achievements in the country’s long-term sustainable development. |  |  |  |
| Local and national capacities are strengthen for the formulation and implementation of climate change policies | $7,768,828 | - PV grid connected projects been beneficiated with economic stimulus coming from the Law of Use of Renewable Energy and Financing of the Energy Transition. - The project will continue with the actions focused in foster the credit availability for grid connected systems. One specific action is to carry out of a one day workshop with the participation of the National Development Bank (NAFIN) , the PV Industry and the Commercial bank. - A Diploma Course on PV Grid Connected Systems in collaboration with the Autonomous University of Yucatan, A Diploma Course in course in central Mexico to be terminated (Queretaro or San Luis Potosi) - Training material for a short course on PV Grid connected systems for technicians. The course will be developed for 2 days duration with a lot high hands on content. - Study report on electricity cost for Grid PV connected systems for high electricity consumption users for Mexicali city area. - By the end of 2010 it is planned to have at least 825 MWh/year generation with PV grid connected systems. - The Energy Regulatory Commission could release the revision of the Interconnection Contract Model for solar sources in which the maximum permissible system size will be risen up to 500 kW and medium voltage. - The first commercial system partially financed by the GEF-PNUD is in operation, and should motivate another private companies or government institution to install PV grid connected systems to generate partially their electricity needs. - Motivation commercial banks ready to start with credit lines to finance home size grid connected PV systems motivated by the PV systems price fall showed during the last 18 months. - Keep monitoring the PVGCS of the Green Corner, Las Palmas in La Paz Baja California Sur, The 150 kWp system installed by Grupo Persal in Mexicali , and the that systems installed at the Regional Wind Energy Center at la Ventosa Oaxaca. - Interconnection guides developed and printed. This material will be distributed in events such as conferences, Colloquiums, and Diploma courses. Also the material will be available in electronic format through the project web page. - Diploma Course "PV Grid Connected Systems", on line trough the Project Web Page, with a promotional campaign to reach nationwide generation and distribution offices of CFE. - Third International Colloquium for the Promotion of the Grid Connected PV Systems to be held in (Queretaro or San Luis Potosi). If the interest on the theme remains it will be held the 4th edition of the colloquium in San Cristobal de las Casas Chiapas. - Keep alive the interest and participation of the National PV industry, and overpass the 100 companies participation registered during the last colloquium edition in Mexicali. If ready the training material for short course for technicians, carry out a pilot course during the last part of 2010. - Adoption and effective enforcement of new legal and regulatory provisions promoting sustainable SWH market. - Annual sales of SWH system - Level of marketing, product and installation services available in the market. - Share of supply side entities adopting the proposed quality control schemes. - Level of customer satisfaction with the installed systems. | - The project carried out its 3nd international Colloquium on grid connected photovoltaic systems with the participation from 200 participants among enterprises, government agencies, academics, and financial institutions, where all stakeholders exchanged and explored different mechanisms to improve the photovoltaic market in Mexico. This event was held by the government of Queretaro who are highly interested in the development of this technology within the state through the different industrial clusters. - On the second quarter 2010, the Energy Regulatory Commission issued the Model Interconnection Agreement for Renewable Energy and Power Cogeneration System in Medium Scale (500 KW). In the same resolution, it replaces the Model Interconnection Agreement for Solar Power Source for Small Scale Model Interconnection Agreement for Renewable Energy Sources and Cogeneration System in Small Scale (30 KW). In April 2010 the CRE issued the new model of contract. In this version the allowed capacity was raised up to 500 kW, and allowing the interconnection in medium voltage. - During the first quarter of 2010, begins the monitoring of the PV system installed at is installed in the Regional Wind Technology Center. The real-time information is published on the project website IIE-UNDP. - The grid-connected PV system Diploma course was organized jointly by the Electrical Research institute (IIE) and the Yucatan Autonomous University (UADY). The course was held in the city of Merida. Among the participants, it outstands the attendance of three engineers of the Federal Electricity Commission (CFE) from the following areas: rural electrification, planning, and electric power distribution. - Following the interest this has generated a graduate, prepared the first draft version of the virtual diploma to allow participation of national and Central America enterprises who have shown interest in training. - It continues with the adaptation of the diploma course on material formatted for PV systems provided on a face to remove to their use for a virtual diploma as part of strategies to increase the participation of technical staff of CFE in graduate courses. It has been The contact with UNDP´s Virtual Scholl to explore the possibility of prepare the virtual diploma and to offer this training through its platform. This will be decided during the first quarter 2011. - A grid-connected PV system User Guide for low scale applications has been developed. The guide will provide residential and commercial consumers with basic information and available resources to lead them to the process of buying a grid-connected PV system. This guide is not attempted to be a technical guide for designing o installing a system. It will mainly include the following topics: technology generalities, site and installation, costs, incentives (net metering, tax benefits, and financial support), suppliers, and interconnection arrangement and contract. - As result of damages suffered the buildings of Industrial Persal occurred in Mexicali City In April 2010, declaimed its opportunity to receive the financial support GEF-PNUD-IIE project to install a 150 kWp PV system., that was because their priorities were focused in repair all the damages caused during the earthquake. The project steering committee agreed to see for new partners. - Up to date, the project leader hold talks with Livestock Producers Association in La Laguna Region Northern region of Mexico. Also some meetings have been held with the Government of the State of Querétaro for the installation of PVGCS system at the international airport of Queretaro city. The counterpart on this is the Secretary of Sustainable Development (SEDUVI). In this initiative the proposed system size is at least 350 kWp, the project will contribute with 50 kWp, and also with the infrastructure and data acquisition system needed for monitoring the system. The Queretaro State government and all the airport partners should contribute with at least 300 kWp. At this moment they are exploring possibilities for this part of the project with national and international financing institutions. - Other alternative for installing the PV systems has been explored with the National Utility CFE. The application tough was with the Distribution branch and the system could be installed within a Distribution Sub-station reaching saturation level. This application could open a broad niche market within the electric company. The financing of the system in this alternative could come from the financing mechanism used by the utility. - In order to complete the result 1 outcome 2 of the project (150 kW grid Connected system) will need to maintain active the project during 6 months extra to finish all the process of installing , incrementing, and system follow up. - Approx. 1,500,000 m2 of SWH has been installed in 2010 in the residential sector. These estimations are based on information from suppliers, and program implementation from INFONAVIT “Green mortgages". During COP16, Present Calderon declares that all mortgages given by INFONAVIT will be “Green”, which represents a huge opportunity for the installation of SWH in the residential sector in the coming years. - During the third quarter of 2010 some key studies have been developed for the analysis of the existing regulatory framework. The results indicates that even when there is an existing robust framework, there is a lack of knowledge of the population as to the application of the laws which needs to be addressed with municipal as well as state governments in order to establish processes tending to the creation of regulatory framework which has to be completed in order to implement existing federal laws. - Existing fiscal incentives have been identified and analysis has begun with the collaboration of members of PROCALSOL's Coordination Unit. - Working groups were established with the participation of the project in order to elevate the status of the DIT to a voluntary norm. Even though the scope of this norm is limited to the evaluation of gas consumption reductions, it will serve as one of the milestones of SWH certification when published during the second quarter 2011. The DIT has been applied to roughly 60 SWH suppliers and close to 90 products. - A work plan has been established with Mexico City's government in order to analyze the implementation of the existing norm into building codes. Specific workshops will be developed in order to promote the use of the norm and analyze possible improvements specially through observance of the norms, and the monitoring of the accomplishments of the regulations. Additional municipalities have been identified and commitments have been established with the government of Jalisco and Guerrero in order to promote in an integral fashion the development of local frameworks and building codes, pertaining the use of SWH. - A web site was developed for PROCALSOL with the support of the project www.procalsol.gob.mx. The Initiative developed a blog validated by the Steering Committee of the PROCALSOL and will be operational shortly. - The initiative has taken part in congresses developed by the National Energy Commission Network (Red Nacional de Comisiones de Energía) in two seminars, promoting the development of local legislation at both state and municipal level. - A workshop was carried out during the third quarter 2011 with the participation of relevant associations which congregate SWH suppliers. Preliminary agreements were taken in order to develop a campaign beginning in 2011, with the support of relevant public entities such as SEMARNAT and SENER. - During 2010, meetings were carried out in preparation for a mission of UNEP officials regarding the development of financial mechanisms for the use of SWH. These meeting with institutions such as the Mexican Banking Association, Nacional Financiera, FIRA, and FIRCO, key public financing institutions, presented SWH as a product which requires specific attention from the financial sector. Commitments were achieved with FIRA, FIRCO and NAFIN for the development of a risk assessment tool to identify potential in the SWH market. |
| UNDP Contribution: The CO supported the Mexican government to develop national and institutional capacity for climate change, with special emphasis on strengthening multi-stakeholder dialogue tools, monitoring and evaluation tools, as well as a strategy in the forestry sector agriculture. This allowed facilitating the implementation of public policy on climate change in order to meet the mitigation and adaptation goals defined in the Special Climate Change Program. The CO also supported the working group of the Inter-ministry Commission on Climate Change (CICC) to develop adaptation policy framework. The working group produced a document that reflect the adaptation efforts in different sectors and lays the foundations for a vision on adaptation to climate change in Mexico. This document also represents UNDP’S important contribution into the design process and implementation of National Adaptation Policy, which was formulated during 2011 and 2012. In terms of the disaster risk reduction, the combination of a policy formulation and local action approach, with a multi-actor at the meso-level methodology, allowed creating crosscutting inclusion of DRR at the national- and state-level development policies, but also enforcing changes through capacity building, institutionalization and dialogue forum with different stakeholders all the way down from the Federal sphere to the local. |  |  |  |
| Gender equality policies have been strengthen | $3,965,868 | - The establishment of an adequate project structure, including the coordination team and specialized consultants. - Quarter and annual reports. - Number of designed specialized indicators. - Evaluation of the existent quantitative and qualitative data in order to establish information priorities. - At least one alternative methodological proposal to develop information on different indigenous issues. - Number of workshops and seminars. - Number of participants and regions benefited by these events. - Protocol of implementation of laws, proposals for monitoring, monitoring and evaluation of LIGIMH. - Proposals for legislative packages in the participating state. Validation meetings of the proposals in each participating states. - Protocol of implementation of laws in each participating state. | - The Indigenous Peoples´ Human Development Index has been launched in October 2011 . - A negotiation with UNICEF and Secretaría de Educación Pública is in progress in order to publish the children´s version of the Indigenous Peoples Monographic. The electronic version has been finished and the first chapters are available in CDI and UNDP websites. - Eight protocols designed and presented regarding implementation of laws for monitoring and evaluation of the national legal framework at the Federation, Guerrero, Zacatecas and Estado de México. - Protocols designed and implemented regarding health and education at the Federal Level. - Legal harmonization package and communication strategy developed to be implemented within public administration campaign through a collaboration agreement signed with the Ministry of Interior. 4. Coordination of an evaluation performed by UNDPs regional center to social dependences in Zacatecas. 5. E-Indicator System developed and implemented in Chiapas. |
| UNDP Contribution: UDNP focused on mainstreaming gender perspectives within programmes/projects in all of the thematic areas. The work carried out on equity has centered its analyses on indigenous peoples and its advocacy on women's political representation. UNDP has pushed for indigenous political participation in the run-up to the 2012 national elections. On women's political representation, together with UN Women and national counterparts, it advocated for parity, strengthening quotas, and promoted the good use of women leadership training funds within the political parties. UNDP also partnered with the GoM to analyze sexist stereotypes produced by institutional advertising, offering best international practices on gender-sensitive publicity. It also promoted a campaign on water as a (women's) right, an important factor of non-discrimination, access to education and limitation of fatigue related to house chores. |  |  |  |
| Democratic institutions are stronger | $19,996,413 | - Indicators on institutionalization of social programs on construction - Accompaniment of federal and state authorities to revise the effectiveness of public services and specially those related to health and education - Number of cultural organizations that assist to the participation exercises. - Number of cultural programs analyzed. - Academic activities and fora organized to increase the dissemination of the Human Development Approach on cultural public policy. | - Activities and monitoring of 798 social programs within the 32 federal entities performed. - Survey sent to crucial governmental actors to update the information of social programmes. Press conference held, in order to present preliminary results of the platform and to highlight the impact of this information on 14 states that went through an electoral process in 2010. - On line platform launched and active, currently measuring indicators that cross-cut social programs and the achievement of the MDGs locally - The diagnosis to identify indigenous social and political participation level on three Mexican states (Chiapas, Oaxaca and San Luis Potosí) is on track. In the first draft (attach) there is identification of liderazgos medios and of indigenous women as focal points. - The municipal agenda proposal Indigenous government and provision of services in indigenous municipalities in the State of Chiapas, Mexico has been approved by the project board and translated to English. UNDP is analyzing the best strategy to implement some of the document´s findings in Chiapas or in other Mexican states. The process has been developed from the indigenous people´s rights perspective. - In order to create this proposal the project team prepared workshops in three municipalities in Chiapas (San Juan Cancuc, Huixtán and Sitalá) - A proposal of the capacity building process on indigenous women´s leadership is on track. This document will taking into account the inputs of the diagnosis and the agenda proposal. The workshops and/or seminars will be held during 2011 in order to promote greater citizen participation so as to build citizenship and improve decision-making processes that would provide more inclusive and effective municipal services. - The International Seminar on indigenous women´s political participation and leadership´s report is available at www.undp.org.mx - The printing and editorial process to publish five studies on political participation and leadership of indigenous women in the Latin American Region (Guatemala, Bolivia, Ecuador, Nicaragua and Peru) in on track. The editorial processed took more time than expected and the project board approved the modification in the work plan. - A diagnosis document on conflict resolution between the indigenous system and the Mexican State on electoral matter started in November and the first products will be delivered on march 2011. Concerning the legislative harmonization process it will began during the first quarter of 2011. The negotiation process with the Electoral Court of the Federal Branch and the Regional Branches was difficult considering the electoral processes in 2010. - Mexico City Cultural policies were analyzed and a Guide was written. 100% accomplished - Five papers divided into two series were published. One named “Culture and Human Development” and the other one “Economics and Culture”. Each paper focuses on Mexico City. 80% accomplished - A seminar on Human Development and Culture was carried out in the National University from January to May 2010. Each panelist wrote a paper, in total 12 documents were written and complied into a book named “Freedom to choose: Culture, Communication and sustainable Human Development”. 100% accomplished. |
| UNDP Contribution: UNDP has played a key role in strengthening democracy in Mexico through electoral observation and monitoring the operation of social programs in the electoral context. In recent years, UNDP has accompanied the Mexican electoral institutions in South-South cooperation, documenting Mexico's experience as an international best practice in this sector. UNDP also has supported capacity development of civil society to influence public policy and strengthening public spaces for citizens’ participation in order for citizens to increasingly play their roles as protagonists of democracy and central subjects of political and social action. UNDP has focused part of its work on the sub-national level as state policies matter increasingly for the well-being of the population. UNDP supported the development of two databases: one encompassing 1,100 federal/local social programmes to measure the multiple dimensions of social policies, and the other to measure local governments’ performance in the accomplishment of MDGs. Both databases are designed with an evidence-based approach focusing on the linkages between good governance and effective pro-poor policies. In addition, UNDP has signed agreements with 9 States with lower HDI. It has continued working in Yucatan on DRR among communities; in Chiapas on peace and dialogue in post-conflict areas; water and sanitation (also in Veracruz and Tabasco); in Zacatecas, Guerrero and Oaxaca on transparency and accountability of government; in Quintana Roo on renewable energy and resilience in the face of Climate Change. |  |  |  |
| Mexico has improved his south-south cooperation mechanisms. | $3,397,375 | - Number of meetings, seminars and fora attended by regional authorities in the framework of the Mesoamérica Project | - A new strategy for assistance to Mesoamérica, strengthened by the SDP projects already operating in El Salvador and in Honduras. - Replication of SDP in a third country in Latin America, and dissemination on information about it throughout other world regions, with the help of UNDP’s LAC Bureau, the regional centre in Panama, and the Private Sector Division in UNDP headquarters in NY. - Presentation launch of the book of Gender and Competitiveness Regional Conference in Panama and at the Merida UNDP sub-national office in the Yucatán Peninsula, and the proposal for follow up publication on the subject with INMUJERES and the European Union. |
| UNDP Contribution: UNDP promoted a regional approach in its south-south cooperation. Mexico presented the MDGs monitoring system during the regional summit "Mechanism of Dialogue and Concentration" in December 2011 which generated great interest among participating countries represented by the Presidents of LA countries. This resulted in a new project to replicate the MGD monitoring system in LA countries with technical assistance from UNDP, was approved and began its implementation throughout 2012. With the experience of electoral assistance since 1994, UNDP Mexico has provided technical assistance to the election process in Egypt, Tunisia, and Libya, and in the negotiation with UNDP Haiti and AMEXCID to strengthen the election process in Haiti. Upon successful implementation in Mexico, Supplier Development Programme was replicated in El Salvador, and is being implemented in Honduras. Additionally, Peru, China and Colombia have showed their interests in the future collaboration replicating the Programme’s methodology. UNDP Private Sector Division recognizes this experience as good practice to assist SMEs to create inclusive employment. |  |  |  |

III. Country Programme Resources

| Focus Area | Programme Expenditure ($) |  |  | % of Total |
| --- | --- | --- | --- | --- |
|  | Regular (TRAC) | Other | Total |  |
| Poverty and MDGs |  | $17,769,127 | $17,769,127 | 18% |
| Democratic Governance |  | $19,996,413 | $19,996,413 | 20% |
| Environment and Sustainable Development & Risk management |  | $58,491,759 | $58,491,759 | 59% |
| South-south cooperation |  | $3,397,375 | $3,397,375 | 3% |
| Total |  | $99,654,674 | $99,654,674 | 100 % |

Data sources: (please indicate the main sources from which data were obtained for this report.)

General Ledger reports: CSA and CDR are the main sources. Year 2012 is already an estimated delivery.

This assessment of results is to be prepared only in the absence of a completed Assessment of Development Results (ADR) for the cycle.